## Slide 1: XFEL LLRF installation
Julien Branlard, for the LLRF team
Phase 1: Pre-commissioning of components
Phase 2: Rack preparation and installation
Phase 3: XTL installation
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: PHASE 1: PRE-COMMISSIONING
Quality control
  Individual component tests (boards, modules)
  Integration tests (crate-level, rack-level)
MTCA crate and boards
    Drivers are installed
    Boards are programmed with correct firmware
    Servers are installed
    Board communication + basic functionality is tested
External modules
    i.e. piezo driver, power supplies
    Power-up , redundancy checks
    Diagnostics / sensor information can be read out

## Slide 3: PHASE 1: PRE-COMMISSIONING
Device test stands
Device tracking
  Labelling
  e-identification
  KDS database entry
Example :
15 minutes / uDWC
x 300
= 2 weeks

## Slide 4: PHASE 1: PRE-COMMISSIONING
All modules tested, ready to be installed in rack
MTCA crate fully equipped and tested
CPIM
PZ16M
LOGM
PSM
MTCA

## Slide 5: PHASE 2: RACK PREPARATION & INSTALL.
Rack assembly and pre-commissioning
XTIN, UG5
Rack assembly and testing area
Cooling water
Ethernet
Mains

## Slide 6: PHASE 2: RACK PREPARATION & INSTALL.
Modify racks
  Top patch panels
  Side patch panels
  Install power outlets (3 phases) (Clarified power distribution with MKK)
  Front-rear openings
  etc…
Installation of hardware
  19” modules
  Equipped MTCA crate

## Slide 7: PHASE 2: RACK PREPARATION & INSTALL.
Inner rack cabling
  RF cables
  Ethernet cables to switch
  Power cables
  No optical fiber yet
At this stage
  All LLRF modules are installed and tested
  Inner-rack cabling done
  Cooling unit check
  Functional tests are done
  Redundancy tests are done
   Ready for tunnel installation

## Slide 8: PHASE 3: XTL INSTALLATION
Moving racks into tunnel
Outer rack cabling

## Slide 9: PHASE 3: XTL INSTALLATION
Connection to mains/ water/ Ethernet
Optical fibers (splicing + patch panel)
Other WP installation (if not done)
 ready for system-level commissioning
Proceed one RF station at a time (following cryomodule installation schedule)
i.e. 2x LLRF racks at a time

## Slide 10: SUMMARY
Installation team:
  Maciek Kudla: organization, inner-rack cabling, incoming inspection, documentation, etc…
  Michael Fenner: Device incoming tests and quality control, etc…
  Bart Szczepanski: Electrical safety, installation, device testing, etc…
  Adam Gallant: Rack installation, pre-commissioning, etc…
  Wojciech Wierba organization, rack infrastructure, outer rack cabling, etc…
Installation schedule goals
  L1 racks ready for end of May
  L2 (3 stations) ready Fall-Q4 2014
  L3 starts in Q1 2015