## Slide 1: Installation of the warm vacuum system
Main Linac Installation Meeting
20.05.2014
Lutz Lilje
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)

## Slide 2: Outline
Installation of cold beam vacuum
  Particle free sections
Installation of Isolation vacuum

## Slide 3: Beam vacuum: Module connection
Main installation task
  Clean room placement
    Space below the modules needs to be empty
    In addition install pump cart
  Installation of the Beamline Absorber (BLA or HOM absorber)
    Connection of two modules
    Leak check and residual gas analysis (RGA)
    Opening the gate valves of the modules
  Removal of the clean room
  Total duration: 1.5 days
    Still needs detailed discussion with cryogenics for optimisation
    Will learn from first string in L1

## Slide 4: Modulmontage XFEL HOM-Absorber
Reinraum aufgebockt und in Höhe justiert mit den beiden demontierbaren Arbeitsplattformen
Courtesy of C. Buhr
Notes: Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 5: Modulmontage XFEL HOM-Absorber
Reinraum zwischen zwei Modulen aufgebaut. Durch die Öffnungen wird von beiden Seiten montiert.
Courtesy of C. Buhr

## Slide 6: Installations for cryo boxes
Final connection similar to modules
  Bellow connections
Currently the installation works on the beamtubes into the boxes should not take place in the tunnel but above ground
If not:
  More time in tunnel needed
  No estimate available yet
  Need at least some time to practise above ground

## Slide 7: Isolation vacuum
Installation of pump carts
  Permanent carts
    2 per cryostring
  Temporary pump carts
    Initially, at least 2 high volumetric flow pump carts
    More details not yet finalised
    Experience in L1 needed
  Leak searches
    Need good coordination with cryogenics group to achieve sufficiently low helium background
      Tests on process piping will ‚flood‘ tunnel with helium

## Slide 8: Pre-requirements for tunnel installation
Necessary infrastructure fully available
  Electrical power for pump carts and mobile clean rooms
  IT network
  Pressurized air for pump carts and valves
  Working platforms especially isolation vacuum works
  (Reminder WP19: Cooling water (ECOLs in chicanes))
No “dirty” works afterwards
All cables (signal and HV for SIP’s) in place

## Slide 9: Installation sequence
Will follow cryogenics to a large degree

## Slide 10: Organization
WPL
Lutz Lilje
Sven Lederer
Section responsibilities:
Lutz Lilje,
Ralph Böspflug
Mechanical Installation supervision
Antonio de Zubiaurre Wagner
Ralph Böspflug
Electronics installation supervision
Dirk Keese
Installation teams from MVS