## Slide 1: Status European XFEL and overview on longitudinal diagnostics
Christopher Gerth
for WP-18 Special Diagnostics
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: Overview on European XFEL
Layout XFEL
Pic tunnel
3.3 km
Photon beamlines
Accelerator tunnel
HERA
PETRA III
Injector
building
FELs / Undulators
35m
Experimental Hall
2nd Workshop at DESY 11/11/2013
Injector building:
7 underground floors
UG7: Injector (≈ 50m)

## Slide 3: Layout European XFEL accelerator
20pC | 4.53ps | 1.46ps | 185fs | 5.23fs
100pC | 4.80ps | 1.55ps | 197fs | 11.6fs
250pC | 5.27ps | 1.70ps | 223fs | 25.4fs
500pC | 6.00ps | 1.96ps | 259fs | 43.0fs
1000pC | 6.77ps | 2.23ps | 303fs | 84.0fs
Energy | 130MeV | 600MeV | 2.5GeV | 17.5GeV
Igor Zagorodnov, 2011
  4 accelerating sections: I1, L1 (4), L2 (12), L3 (84)
  3 bunch compressor chicanes
Tunnel XTL
Injector
Building
XTIN, UG7
  Further beam energies: 8 GeV, 12.5 GeV, 14 GeV

## Slide 4: Longitudinal Diagnostics at European XFEL
20pC | 4.53ps | 1.46ps | 185fs | 5.23fs
100pC | 4.80ps | 1.55ps | 197fs | 11.6fs
250pC | 5.27ps | 1.70ps | 223fs | 25.4fs
500pC | 6.00ps | 1.96ps | 259fs | 43.0fs
1000pC | 6.77ps | 2.23ps | 303fs | 84.0fs
Energy | 130MeV | 600MeV | 2.5GeV | 17.5GeV
Igor Zagorodnov, 2011
BAM
EOD
TDS
BAM
BCM
EOD
BAM
BCM
TDS
BAM
BCM
EOD
BAM
BCM
TDS
BAM
CRISP4

## Slide 5: Timeline and Milestones
2014
2015
2016
2017
2018
SA1
Start user operation
Full TDR performance
1st lasing possible
SA3
SA2
RF gun conditioning
1 year of Injector commissioning
Injector cooldown
First e-beam out of RF gun
Installation of accelerator in tunnel
Gun operation Injector Installation
Linac cooldown
  Start Injector Cooldown: 06/2014  04/2015  05/2015
  Start Linac Cooldown: 07/2015  07/2016

## Slide 6: Development of pulse energy over time:
Gun Conditioning in XTIN (F. Brinker / A. Wagner)
Chart: date
| 9.12. | 10.12. | 11.12. | 12.12. | 13.12. | 14.12. | 14.12. | 15.12. | 16.12. | 16.12. | 17.12. | 17.12. | 17.12. | 17.12. | 18.12. | 18.12. | 19.12. | 19.12. | 19.12. | 20.12. | 20.12. | 21.12. | 21.12. | 22.12. | 23.12. | 23.12. | 23.12. | 23.12. | 23.12.
Pulse Energy [J] | 1.775 | 58.3333 | 375 | 0 | 256 | 1180 | 615 | 590 | 1845 | 1511.25 | 1625.9 | 1950 | 385 | 1713.6 | 2700 | 357.5 | 3250 | 2600 | 3315 | 3250 | 1560 | 3380 | 2970 | 3510 | 2520 | 2500 | 3510 | 3120 | 1968
Goal : 6.5MW ∙ 650µs = 4.2 kJ
Damage of springs for cathode plug
Problems with RF window for operation with 10MW klystron

## Slide 7: Super-Conducting Accelerating Modules
2.2 K forward
40 K forward
2 K 2-phase
cavity
2 K return
80 K return
8 K return
RF main coupler
magnet current feedthrough
5 K forward
4 K shield
70 K shield
Severe problems with cold couplers and welding of He pipes
Start of installation of modules for L1 (XM1 – XM4) in July 2014
From September on every week 1 module to be installed …
17.5 GeV == 25 RF stations
1 RF station (10 MW) == 4 modules
1 module == 8 cavities
1 cavity == 9 cells

## Slide 8: Layout Cryogenics XSE / XTIN
XLTL1 vertical
XLTL1 horizontal
Installation in shaft XSE Feb 2014
XTIN, UG7
Cold boxes
(delayed)
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 9: Installation Cryo Line (02/2014)

## Slide 10: Installation of warm beamline on girders
Radiation
Shielding
Steel/Concrete Sandwich Girder:
4.6 m long, 2.5 t
Electronic racks close to beamline components:
No access during machine operation
Assembly of components on girder in clean room
Girder assembly foreseen for 2nd half of 2014

## Slide 11: Electro-Optical Diagnostics
3 EOD vacuum systems with optic boxes are ready for installation
EOD
‘Mini-girder’ for assembly tests in the lab
Notes: Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 12: Initial E-beam parameters
Quantity | Value
electron energy | 8/12.5/14/17.5 GeV
macro pulse repetition rate | 10 Hz
RF pulse length (flat top) | 600 ms
bunch repetition frequency within pulse | 4.5 MHz 100 kHz
bunch charge | 0.02 – 1 nC 0.5 nC
electron bunch length after compression (FWHM) | 2 – 180 fs 90 fs
Slice emittance | 0.4 - 1.0 mm mrad
beam power | 500 kW 5 kW
Linac will be operated with several tens of bunches (not single bunch) as fast as possible
  single bunch operation is useless for LLRF diagnostics and studies
  many bunch operation is more difficult for machine protection system
beam charge around 0.5 to 1 nC
  Good for diagnostics and LLRF

## Slide 13
Thank you
For your attention

## Slide 14: Ramp-up operation
If main accelerator commissioning starts summer 2016:
hrs | 2016 | 2017 | 2018 | >2018
Accelerator A | 2500 | 4700 | 5600 | 5600
X-ray delivery Tx | <500 | 2800 | 3900 | 4800
Users UNNN | 0 | 2 x 1000 | 3 x 2100 | 3 x 4000
Thomas Tschentscher, European XFEL,
European XFEL Users’ Meeting, Hamburg 29/01/2014

## Slide 15: Super-Conducting LINAC – Time Structure
RF pulse repetition rate: 10 Hz (up to 25 Hz or cw)
Max. RF flat top length: < 600 μs
Bunch frequency: n*111 ns with n ≥ 2 (1 MHz or 4.5 MHz) => bunch trains with up to 2700 bunches

## Slide 16: Overview on WP-18 Devices
16
 | INJ | BC0 | BC1 | BC2 | TL | UND | Sum
BAM | 1 | - | 2 | 2 | 2 | - | 7
EOD | 1 | 1 | 1 | - | - | - | 3
BCM | - | 1 | 1 | 2 | - | - | 4
CRD | - | - | - | - | 1 | - | 1
SRM | - | - | 1 | 1 | - | - | 2
TDS | 1 | - | 1 | 1 | - | - | 3
EBPM | - | 1 | 1 | 1 | - | - | 3
Sum | 3 | 3 | 7 | 7 | 3 | - | 23
TL
7 Completely different types of devices (≈ Einzelanfertigung)
All WP18 devices in XTL and INJ
Most in B1 and B2 section
BC1 Girder Belegung
G2 : EOD, BCM, BAM
G3 : EOD, BCM, BAM
G4 : TDS
BC2 Girder Belegung
G2 : BCM, BAM
G3 : BCM, BAM
G4 : EOD
G5 : TDS
Notes: 16
Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 17: WP-18 Special Diagnostics
EBPM
SRM
SRM
EBPM
THz
BAM
BAM
BAM
BAM
EOD
BCM
BCM
BCM
BCM
TDS
TDS
TDS
EBPM
EOD
EOD

## Slide 18: Longer perspective until mid of 2015
time
energy
Arrival Time
BAM
Beam Energy
BPMs in BC (EBPM)
2 BAMs
E-Spectrometer
Energy Spread
VIS SR Monitor (SRM)
E-Spectrometer
Longitudinal Phase Space
TDS + E-Spectrometer
E0
DE
t0
Dt
Bunch Profile / Length
TDS
EOD
BCM
THz Spectrometer
Incoherent radiation
THz Streaking

## Slide 19: Milestones – Injector
1 year of Injector Commissioning WITH FULL BEAM PARAMETERS
during installation of main linac L1/2/3:
Operation LLRF I1 + A39 and installation
Operation 2-4 Links, BAM, EOD Laser + installation all other devices