## Chain of Activities
Step | Decisions/Information Needed | Preconditions / Tasks | Location | Responsible | Coordinator
Module arrives at AMTF |  |  | AMTF | WP10 | MO
Incoming Inspection |  |  | AMTF | WP10 | MO
Cabling |  | -Connection of RF Cables -Tuner Cables -and others | AMTF | WP10 +various Groups | MO
Installation on Test Stand |  |  | AMTF | WP10 | MO
Warm Coupler Conditioning |  | -Connection to Beam Pipe -Connection to Cryogenics | Test Stand | WP10 | MO
AMTF Test |  |  | Test stand | WP10 | MO
Cool Down |  |  | Test Stand | WP10 | MO
Cold coupler Conditioning |  |  | Test Stand | WP10 | MO
Low Power RF Test |  |  | Test Stand | WP10 | MO
HighPower RF Test |  |  | Test Stand | WP10 | MO
RF Control Test |  |  | Test Stand | WP10 | MO
Magnet Test |  |  | Test Stand | WP10 | MO
Warm Up Test |  |  | Test Stand | WP10 | MO
Cryo Load Test |  |  | Test Stand | WP10 | MO
Module Acceptance |  |  | Test Stand | WP10 | MO
Waveguide Tailoring | -Waveguide Spec (CO) -Module RF Config, right/left (MO) |  | AMTF? | WP01 | MO
Storage |  |  | AMTF | WP10 | MO
Waveguide Assembly and connection |  |  |  | WP01 | MO
Storage |  |  | AMTF | WP10 | MO
Transport to Tunnel | RF Sring configuration (TBD: WP16?, HW?) | -Connection Waveguides Installation (WP01, WP32) -Ceiling Frame Installation (WP33) | through XSE, XTL | WP33 | MO
Connection to Ceiling Frame |  |  | Tunnel | WP33 | TC
Alignment |  |  | Tunnel | WP32 | TC
Module Connections (Beampipe, Cryo) |  |  | Tunnel | WP03, WP08 | TC
Leak Checks of String |  | String Complete | Tunnel | WP03 | TC
RF Station Installation |  |  | Tunnel | WP01 | TC
Waveguide Connections |  |  | Tunnel | WP01 | TC
RF Station Commissioning (Load) |  | Infrastructure complete | Tunnel | WP01 | TC
Interlock Checks |  |  | Tunnel | TC | TC
Warm Coupler commissioning |  |  | Tunnel | WP05 | TC
End Point: Ready for cooldown |  |  | Tunnel | TC | TC