## Group Meeting to do List
| Attendees | CIE Group Meeting / To Do List |  | actual cw | actual date |  |  | LB changes 070814
|  | August 6th, 2014 |  |  | 2026-08-05 | 2026-08-05
| Task / Topics | Comments / Problems / expected Output | Resp. | Involv. | Start | Target | done
| Job Training / Getting experiences |  | T | T | T | T | T
| SE 3D CAD |  | Osa |  | 2013-02-26 | 2013-03-18 | done
| SE 3D CAD |  | Lba |  | 2013-02-26 | 2013-03-19 | done
| Beckhoff Training | booking hotel/flight/attendance at the training in progress | ALa |  | yes | 2013-04-20 | done
| KDS Basic & Administration |  | ALa |  | yes | 2013-02-06 | done
| Get familiar C++ Programming | (Beckhoff mainly used progr. language) in progress - almost completed | ALa |  | yes | 2013-06-01 | done
| SE 3D CAD ST5; EDMS; |  | VLy |  |  |  | done
| Sharepoint Revisioning Training; ST5 Update Training | postponed until when??? | all CIE | all | no
| new Sharepoint Administration Training |  | NRe |  | no
| ANSYS Training |  | all CIE | all | no | in 2014 | done
| Organization |  |  |  |  | T
| define, what meetings shall be attended by which CIE member | to be discussed also with the Leading Scientists and S. Molodtsov | WTs | Ala;Lba;Osa | 2013-01-15 | 2013-02-04 | done
| establish CIE Group Meeting and Minutes |  | WTs | Nr;Ala;Lba;Osa | 2013-02-04 | 2013-02-04 | done
| clarify details of cooperation with DAQ and CIE | in progress. Details to be clarified among TC, CIE and DAQ; E-Plan??? | ALa | WTS | Yes | 2014-01-25 | done
| Assign Attendance of Meetings |  | WTs | Nr;Ala;Lba;Osa | yes | 2013-02-12 | done
| define interface WP73 and Endstations | defined according to SMo: responsibility stays devided | WTs |  | Yes |  | done
| define interface Procurement / CIE |  | WTs |  | 2013-03-04 |  | done
| Recruit mech. Engineer | in progress | WTs |  | Yes |  | done
| Assigned Tasks |  | T | T | T | T | T
| propose Device Lists and Device Diagrams with Function-Icons as pattern for all Experiments | Presentation on the next meeting with the leading scientists | Lba | WTs | yes | 2013-02-11 | done
| finalize a 3D Model of the interface(s) between WP73 and the Exp. Hall in close cooperation with all groups involved |  | Osa |  | yes | 2013-03-28 | done
| finalizing CAD models for the SPB-TDR |  | Nre |  |  | 2013-03-28 | done
| Clarify usability of QR-Codes for general labelling | Presentation on the next meeting with the leading scientists | ALa |  | yes | 2013-02-11 | done
| Make an independent cross check of the beam lines starting with the empty experimental hall and the specifications by W. Graeff. | TC | Osa | TC Tobias Haas | ? | ? | done
| Diagn. Devices: develop framework for assessment | diagram with diagn. devices for each Instrument | Lba |  | yes |  | done
| Diagn. Devices: collect requirements ; write specification | writing specification is not applicable | Lba |  | yes |  | done
| Alignment Laser (ALAS) : collect requirements; write specification(s) | has been switched to a Batchelor Thesis for Christian Dauer | CDa | WTs | yes
| SLIT/ATT/CRL Specifications:Collect and document |  | Lba |  | yes | DONE | done
| Get familiar with the DAQ test methods | ongoing ( not limited) | ALa | Nicola Coppola | yes |  | done
| Finalise IKC02 Slits and attenuator technical documentation | [5 empty] | done
| Prepare IKC02 CRL technical documentation |  | LBa |  | yes | 2014-02-14 | done
| Vacuum parts: list for each instrument | requires P&ID and vacuum component list for all instruments | OSa | LBa | yes | 2014-02-14 | done
| Vacuum P&ID: Design for each instrument | Process Diagrams: First Drafts done (exception: SCS) | Lba |  | yes |  | done
| Vacuum P&ID: Design FXE | Process Diagram First Draft | Lba |  | yes |  | done
| Vacuum P&ID: Design for SPB | Process Diagram First Draft | Lba |  | yes |  | done
| Vacuum P&ID: Design for MID | Process Diagram First Draft | Lba |  | yes |  | done
| Vacuum P&ID: Design for HED | Process Diagram First Draft | Lba |  | yes |  | done
| Vacuum P&ID: Design for SQS | Process Diagram First Draft | Lba |  | yes |  | done
| Vacuum P&ID: Design for SCS | Process Diagram First Draft | Lba |  | no |  | done
| Gas and water P&ID: Design for each instrument | in conceptional phase | (Lba) |  | yes
| Inst. electrical system schematics: Develop template/questionnaire | FXE / develop formats of a list /Eplan | Ala |  | yes |  | done
| SASE3 instrument slits | specification complete, preliminary concepts ready | Lba |  | yes
| SASE3 special slits (inside KB chamber) collect requirements | specification and conceptual design | Lba |  | no
| Prepare Specifications for a static Imager/ colimator for SCS | specification and conceptual design | LBa |  | yes
| SQS beam imager | specification and conceptual design | Lba |  | no
| Prepare Specifications for a Pulse Picker | Redesigned absorbing rotor and housing | LBa |  | yes
| Pump Carts Specification and Procurement | ongoing | Osa |  | yes
| Laser Chicanes:Final Design, Production and Documentation of all | take over concept from CDa | OSa | CDa / WTs
| Cabling Chicanes Estimation and Simulation |  | Osa | ALa | yes
| Presentation of a Standardize Device Cabling | planed example: FXE von Hamos Spectrometer | ALa |  | no
| XOBT:XHEXP interface Design(Shielding) and Production |  | Osa | WP73 | yes
| Vacuum System Layout | PID; BOM; Calculations/Simulation with VACTRAN / MOLFLOW | Osa |  | yes
| MID Vacuum Layout | Calculation on request | Osa |  | yes | 2013-10-30
| SPB; DP design + external Roughing pump Design | ongoing (VACTRAM, Molflow) | Osa |  | yes
| SCS ; initiating meetings to collect requirements for DP and vacuum system | starting week 44 | Osa |  |  |  | done
| Exp. Component List: Present Technical Meeting | ongoing | WTs | OSa; LBa | yes | 2014-01-15
| write two chapters for SPB-TDR |  | Nre |  | yes |  | done
| design vacuum chamber for SPB | ongoing | Nre |  | yes
| mechanical integration for SPB | ongoing | Nre |  | yes
| lab and hutches infrastructure planning for all Exp. hutches | mayor task | Nre |  | yes | 30.11.13 | done
| drawing Ref. Marks into Hutches | check with DESY (MEAII) | Nre |  | yes
| Determine FXE Beckhoff terminals |  | ALa |  | yes |  | done
| Define KDS inputs |  | ALa |  | yes |  | done
| determin next steps for terminals | NC define rules (waiting on DAQ) | ALa |  | yes |  | done
| collect requirements of all Exp. Groups about general Vacuum Components and prepare and present a catalogue of Standard Components | including especially the differential pumping (check with WTs) | Osa | WTs; LBa | yes | 2013-08-25 | done
| initiate a meeting with all involved scientists/engineers about CRLs |  | Lba | WTs |  |  | done
| Cables labelling | surveyed available solutions. | ALa |  | yes |  | done
| develop common understanding about CRL "Philosophy" | Hard stopp V-Groove or free movement | Lba | WTs | yes |  | done
| Roll out E-Plan and organize the Training |  | ALa |  | yes |  | done
| Introduction of ePlan in place of KDS | Feedback from IT | ALa |  | yes | 2013-10-30 | done
| electrical/electronic software selection | in conjunction with DAQ - related to ePlan usage or not | ALa |  | yes | 2013-06-01 | done
| developement of an Electrical Documentation Strategy | to be presented in TM meeting DEC 6th | ALa |  | yes |  | done
| explain/document measurements for the Hutch-3D-Models | Wall thicknesses; space for shielding, infrastructure etc. (check with Nico) | Nre | WTs
| collect requirements of all Exp. Groups about the Beamstops | prepare a presentation about specifications | VLy | WTs | Yes | 2013-08-31 | done
| Control System for Test Vacuum Chamber (WP79) | Working with S.Bari, N.Coppola, J.Schulz | ALa | N.Coppola, S.Bari | yes |  | done
| Liquid Jet Control (WP79) | Working with S.Bari, N.Coppola, J.Schulz | ALa | N.Coppola, S.Bari | yes |  | done
| Beamdumps: design | Problems with B4C durability against focussed X Ray : new simulation necessary | VLy | WTs | yes
| FEM analysis of thermal load of SASE1,2 beam for different incidence geometries. |  | VLy | WTs | yes
| Part 1: simplified model | of the absorption volume (uniform cylindrical distribution of photons) | VLy | WTs | yes |  | done
| Part 2: refined model | of the absorption volume (Gaussian/exponential distribution of photons) ongoing | VLy | WTs
| Prepare a report of the Machine Directive Seminar in Nov. 13 in Dortmund | postponed / collaboration with safety (SK) | WTs | SKo | no | 1.12..13
| Write CIE contribution to the annual Report 2013 |  | WTs | CIE | yes | 2014-01-06 | done
| Prepare a report of "Standardization" for the SAC Meeting in March 14 | was not needed | WTs | CIE | no | 2014-03-01 | done
| Collect requirements for the Laser Chicanes |  | CDa | Guido Palmer | yes |  | done
| Define Pump Carts (Specs and Qty) for all Instrument Groups |  | OSa | LBa | yes |  | done
| Coordinate the Cable Lenght Definition for XHEXP1 | To be discused with TC and DAQ | ALa | DAQ | yes |  | done
| Help SQS and MID with Hutch Design |  | NRe |  | no
| General Tasks without special target date |  | T | T | T | T | T
| all detectors electrical and network integration | ongoing | ALa |  | yes
| Motor axis: collect from SPB/SFX FXE | crosscheck compatibility with Beckhoff controller | ALa |  | yes
| Support for Solid Edge; questions concerning suppliers and DESY |  | Nre |  | yes
| ePlan SWOT Analysis | SWOT analysis regarding the usage of ePlan instead of KDS / WSCAD combination | ALa |  | yes | 2013-05-15 | done
| define Beckhoff Crates for Racks | in progress - samples ordered | ALa | N.Coppola | yes |  | done
| XOBT:XHEXP interface Coordinates | ongoing | Osa | WP73 | yes
| Requested Tasks not assigned yet |  | T | T | T | T | T
| WP86: Static Imager : CIE is asked to collect requirements | Only SCS require these devices |  | Lba | yes |  | done
| WP86 : soft X-Ray slits: CIE_LBa is asked to collect requirements |  |  | Lba | yes |  | done
| WP86 : Laser Incoupling: CIE is asked to collect requirements |  |  | Lba | yes |  | done
Mechanical integration of DSSC AGIPD
| Answer the Questionaire of the Survey department? | TT stated that the Experimental Groups themselves should take care of that! |  |  |  |  | done
| Topics brought up by visitors |  | T | T | T | T | T
| known absence next two weeks | CIE Staff
ALa | August 2nd to August 31st: Vacation | Antonios Lalechos
LBa |  | Lewis Batchelor
CDa | Contract ends August 8th | Christian Dauer
NRe | August 4th to August 22nd Vacation | Nadja Reimers
OSa | July 24th to August,17th Vacation | Osama Salem
VLy |  | Viktor Lyamayev
WTs | July 28th to August,1st Vacation | Wolfgang Tscheu
| Colour Code for Tasks: | Colour Code for Dates
| Needs reworking, more detail, updating, confirmation, verification etc. | in time
| New Tasks | delay
| Review Times | future
Title

## Plan of Procedure
Tasks /Steps | Task description | Documents to be delivered | Wo is responsible for delivery ¹) | where to find Definition / Explanations /Descripion
Definition and description of the task | Input: Definition of preliminary Budget and Rescources and Time/Timeslot planned for the task. | Project Budget Plan Project Schedule | WP8x; {Finance/Controling} | WP8x Planning?
Research | Documenting the scientific background and state of the Art. | CDR / TDR | WP8x | Project Handbook
Preliminary Assignment to CIE | Information input | Preliminary Project Order | WP8x | informal? Email?
Conceptualization | developing a concept | see Mandantorys docs of the CDR and TDR | WP8x; {CIE} | Project Handbook
technical | collect ideas, | Concept Description | WP8x; {CIE} | CIE:informal? WP8x: TDR
organizational (capacity/budget/time schedule) | descibe boundary conditions | Project Budget Plan Project Schedule | WP8x; {Finance/Controling} | WP8x Planning?
Feasibility assessment | Simulations / Calculations / Pre-testing | Documented evaluation | WP8x; {CIE} | informal?
Establishing the design requirements | write down all needs and wishes and boundary conditions | Black Box etc. | WP8x; {CIE} | Requirements /Specification: to be defined by CIE/WP8x
Design Review | organize | see Design Review | WP8x; {Stakeholder} | Project Handbook
Final Assignment to CIE |  | Final Project Order | WP8x | informal? Email?
"state of the art" research | search for and evaluation existing solutions | documented considerations | CIE ; {WP8x} | informal? Email?
Make Design (M) or buy (B) decision | decide |  | WP8x; {CIE} | informal? Email?
CFT and Order for Supplier ( if applicable) | prepare MB proposal / get decision | CFT / Order | Procurement; CIE ; {WP8x} | https://www.xfel.eu/internal/procurement/index_eng.html
Preliminary design | develop and document specifications | Models, Drawings, El-Schematics | CIE | Solid Edge / CIE Specifications Form/Design Directive / VDI2221/E-Plan
Detailed design /documentation | detailed specifications (mechnical and electrical) | Models, Drawings, El-Schematics , design approval | CIE | Solid Edge / CIE Specifications Form/Design Directive / VDI2221/E-Plan
Prototyping / approve functions | realize main functional parts and test them |  | CIE | Hardware
Production Readiness Review | organize | see PRR mandatory documents | WP8x; {Stakeholder} | Project Handbook
Make Production (M) or buy (B) decision | decide |  | CIE ; {WP8x}
CFT and Order for Supplier ( if applicable) | prepare MB proposal / get decision | CFT / Order | Procurement; CIE ; {WP8x} | https://www.xfel.eu/internal/procurement/index_eng.html
Production planning |  | Production Plan | CIE; {Contractor} | tbd
Production |  | Quality control documents | CIE; {Contractor} | see CIE design directive
Testing (incoming tests) |  | documented test results | WP8x; {CIE} | see CIE design directive
Installation |  | Installation Plan | WP8x; {CIE};{Contractors} | tbd
commissioning: putting into operation / start up | aprove and complete manuals and other documentation | Operation Manual,Documentation, Electrical Schemes etc | WP8x; {CIE} | tbd
(final) operation (phase) | operate the Instrument | tbd | WP8x | tbd
maintenance | tbd | tbd | n.n. | tbd
extensions | tbd | tbd | n.n. | tbd
shutdown / decommissioning | tbd | tbd | n.n. | tbd
used abbreviations:
CFT= Call for Tender
WP8x =individual Instruments Workpackage
tbd = to be discussed / to be defined
n.n.= not nominated (yet)
¹) Push Principle: party responsible (named first) has to give / to offer information and to make shure the task is done. {party in brakets} should help.

## CIE Meetings
Regular Meetings | Attendence required
| NRa | ALa | LBa | OSa | VLa | WTs
WPG3 (PBS) Meeting | d | d | d | d | d | d
monthly Staff Meeting | c | c | c | c | c | c
TC-Meeting | d | d | d | d | d | d
CIE Group Meeting | c | c | c | c | c | c
CAD Integrations Meeting | d |  |  |  | d | d
CAD SE Anwenderforum | d |  |  |  | d | d
xfel-wp76-hw-to-daq-integration |  | d |  |  |  | d
Group Leader Meeting | [5 empty] | c
Attendance
| c | compusory
| d | discretionary

## LogBook
Change Record
(started 25.2.13)
2013-02-25 | WTs | added Table "CIE Tasks Requested"
2013-06-12 | WTs | Requested Task added to GM list
2013-06-12 | WTs | Visitors added
2013-06-12 | WTs
2013-07-24 | WTs | discarted the CIE Report line
2013-07-24 | WTs | Integrated codes an abbr. into the Mainlist
2013-08-13 | WTs | added Viktor
2013-10-24 | WTs | added tasks from LBa
2013-10-25 | WTs | Convention:name subject of task first, then the action
2014-05-21 | WTs | some minor changes to the Sheets
2014-08-05 |  | impemented the "Plan of Procedures"

## Participants List
Ansaldi | Gabriele | AER17/505 | 6965 | AGa | Ansaldi Gabriele,
Appel | Karen | AER17/503 | 2930 | KAp; | Appel Karen, | x
Aquila | Andrew | AER17/520 | 6924 | AAn | Aquila Andrew,
Bari | Sadia | AER17/532 | 6952 | BSa | Bari Sadia,
Batchelor | Lewis | AER17/406 | 5642 | LBa; | Batchelor Lewis, | x
Borchers | Gannon | AER17/513 | 6970 | GBo; | Borchers Gannon, | x
Bressler | Christian | AER17/504 | 1909 | BCh | Bressler Christian,
De Fanis | Alberto | AER17/522 | 6983 | DAl | De Fanis Alberto,
Deiter | Carsten | AER17/532 | 2439 | DCa | Deiter Carsten,
Delitz | Jan Torben | AER17/512 | 4147 | JDe; | Delitz Jan Torben, | x
Delmas | Elisa | AER17/532 | 6978 | DEl | Delmas Elisa,
Galler | Andreas | AER17/502 | 5609 | GAn | Galler Andreas,
Gawelda | Wojciech | AER17/502 | 5610 | GWo | Gawelda Wojciech,
Kitel | Matthäus | AER17/5 | 6870 | KMa | Kitel Matthäus,
Lalechos | Antonios | AER17/404 | 6973 | LAn | Lalechos Antonios,
Lyamayev | Viktor | AER17/406 | 6990 | VLy; | Lyamayev Viktor, | x
Madsen | Anders | AER17/506 | 5667 | MAn | Madsen Anders,
Meyer | Michael | AER17/524 | 5614 | MMi | Meyer Michael,
Molodtsov | Serguei | AER19/507 | 5779 | MSe | Molodtsov Serguei,
Nakatsutsumi | Motoaki | AER17/503 | 6966 | NMo | Nakatsutsumi Motoaki,
Palmer | Guido | AER19/322 | 6976 | PGu | Palmer Guido,
Reimers | Nadja | AER17/513 | 5341 | NRe; | Reimers Nadja, | x
Salem | Osama | AER17/404 | 5636 | OSa; | Salem Osama, | x
Scherz | Andreas | AER17/507 | 6960 | SAn | Scherz Andreas,
Schulz | Joachim | AER17/519 | 4511 | SJo | Schulz Joachim,
Thorpe | Ian | AER17/509 | 6980 | ITh; | Thorpe Ian, | x
Tschentscher | Thomas | AER19/505 | 3904 | TTh | Tschentscher Thomas,
Tscheu | Wolfgang | AER17/409 | 1451 | WTs; | Tscheu Wolfgang, | x
Zhang | Haiou | AER17/513 | 5608 | HZh; | Zhang Haiou, | x
Freund | Wolfgang | AER19/302 | 5630 | FWo | Freund Wolfgang,
Raabe | Steffen |  |  | RSt | Raabe Steffen,
Dauer | Christian |  |  | CDa; | Dauer Christian, | x
KAp;LBa;GBo;JDe;VLy;NRe;OSa;ITh;WTs;HZh;CDa;