## Slide 1: XFEL Injector Commissioning Plan
Bolko Beutner, MPY
Beschleuniger Betriebsseminar
26.3.2015
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: Global Timeline and Milestones (today)
2014
2015
2016
2018
First e-beam out of RF gun installed at XFEL
Injector cooldown
Injector com. up to full XFEL performance (varying charges and bunch patterns, laser heater, slice diagnostics, intra-train feedbacks, automated procedures)
Linac cooldown
SA1
Initial linac com. with reduced performance
Start user operation
Full TDR performance
Continued accelerator com. to full performance (high beam power, bunch length flexibility, multiple bunch properties per rf-pulse, full wavelength tuneability, ….)
Beam line and experiment com.
1st lasing possible
SA3
SA2
Gun and injector laser com.
. First user operation
e-
g
2017

## Slide 3: Global Timeline and Milestones (today)
2014
2015
2016
2018
Injector cooldown
Injector com. up to full XFEL performance (varying charges and bunch patterns, laser heater, slice diagnostics, intra-train feedbacks, automated procedures)
Linac cooldown
e-
g
2017

## Slide 4: Introduction
Commissioning goals:
Beam quality
  Emittance, …
Stability
  LLRF, beam-based feedbacks, ….
Bunch trains
  Losses, stability along train, …
Reliability
  Procedures, software, hardware, operator training…

## Slide 5: Injector Commissioning
Commission sub-components
  LLRF, RF, ...
  standard and special diagnostics
  magnet systems, fast kickers, ...
Beam Dynamics
Establish routine operation with all necessary procedures, software, …
“Teambuilding”
Time available for tests, detours, „trial and error“, …

## Slide 6: Injector Overview
Dump Transverse Deflecting Structure
Spectrometer Diagnostic Section Laser Heater 3.9 GHz Module 1.3 GHz Module Gun

## Slide 7: Injector Beam Line Components
Magnets | 6 Dipoles, 15 Quads, 20 Correctors, 2 Quad-Movers, 2 Solenoids
Modules | 1.3 GHz, 3.9 GHz
Diagnostics | 15 BPMs of 5 Types, 11 Screen Stations, 4 Toroids, 2 Dark Current Monitors, 1 Beam Arrival Monitor, 1 Beam Halo Monitor, 1 Electro-optical Detector, 3 Faraday Cups
Fast Devices | 5 Kicker Magnets, 1 Transverse Deflecting Structure
Undulator | 1 Laser Heater Undulator
Vacuum | About 50 m of cold & warm beam vacuum, Dark Current Collimator, Beam Stop

## Slide 8: Injector Commissioning: Goal(s)
Achieve all XFEL parameters
Reduced/relaxed parameter set:
  beam charge around 0.5 nC good for diagnostics and LLRF
  Linac operation with several tens of bunches
    single bunch operation is useless for LLRF diagnostics and studies
    many bunch operation is more demanding for machine protection
Quantity | TDR goal | initial goal
macro pulse repetition rate | 10 Hz | 10 Hz
RF pulse length (useable flat top) | 600 ms | 600 ms
bunch repetition frequency within pulse | 4.5 MHz | 100 kHz
bunch charge | 0.02 – 1 nC | 0.5 nC
Slice emittance | 0.4 - 1.0 mm mrad | 1.0 mm mrad
Gun gradient | 60 MV/m | 50 MV/m

## Slide 9: Gun Performance
Reasonable beam quality with reduced gun gradient confirmed in simulations
courtesy E. Kot
Example: 0.5nC |  | Gun50 | Gun60
Working Point | MaxB [T] | 0.1892 | 0.2224
 | XYrms [mm] | 0.360 | 0.285
projected Emittance | e [10-6 m] | 0.544 | 0.439
averaged slice Emittance | eSl [10-6 m] | 0.518 | 0.386
rms bunch length | z [mm] | 1.98 | 1.94
0.5nC

## Slide 10: Bunch Trains
60 to 2700 bunches per train at a 10Hz repetition rate
78 to 3510 W beam power at 130MeV and 1nC (10-472kW at 17.5GeV)
Expected dark current of up to about 30 W at 130MeV and 600 μs
Variable pulse length, repetition rate, and beam-on-demand mode to reduce losses
Orbit/energy stability along train (intra-train feedbacks)
Enables semi-parasitic diagnostics (emittance, …)

## Slide 11: Initial e-beam parameters – Bunch Repetition
Linac will be operated with several tens of bunches (not single bunch) as fast as possible
RF pulse length can be varied (gun performance and dark current losses might be limiting factors)
Initially possible repetition rates (injector laser)
Many bunches make European XFEL unique
Should be established as soon as possible
n | bunch repetition frequency [MHz] (=1.3GHz/(n*144) with n>=2 and even) | bunch spacing [ns] | max # of bunches in 600 μs train
2 | 4.514 | 222 | 2700
3 | 3.009 | 333 | 1800
8 | 1.128 | 886 | 670
90 | 0.1003 | 10000 | 60
- | - | - | 1

## Slide 12: Commissioning Phases
Start | July 2015
Initial Commissioning Phase Goal: Reproducible and reliable beam transport for full bunch train length from the gun to the injector dump | 10 weeks
Intermediate Commissioning Phase (minimum goal) Goal: Slice emittance is reproducible below 1mm mrad | 20 weeks
Final Commissioning Phase Goal: Nominal performance for all charge options and full bunch train length | 19 weeks
Optional Beam Physics Studies / Contingency Beam physics studies and improvement of performance beyond TDR goals… | 6 weeks
End | June 2016
Initial parameter set
Full TDR parameter set
Operation consolidation at the end of each phase
  “Hot” tests (e.g. recovery after emergency shutdown)
  Stability runs (one week without interference…)
  Procedures, operator training, software
  Goal of each phase is only reached if it is reproducibly achieved

## Slide 13: Example: Detailed Sequence

## Slide 14: Initial Commissioning Phase
In the first beam phase we will focus on basic beam quality only (0.5nC, 60 bunches per train, no optimised emittance,…) but full transmission to allow for beam-based commissioning and calibration of all subsystems.
Goal: Full transmission is reproducible
Requirements: Stable and reliable operation of subsystems

## Slide 15: Initial Commissioning Sequence
Gun setup
LLRF commissioning w/o beam
Initial operation of standard diagnostics
ACC1 acceleration setup
Laser heater dipoles for basic energy setup
Orbit control (automatic orbit steering)
Optics setup / Destructive emittance measurements
Machine protection system (MPS) for 600 μs trains (tests, threshold calibration)

## Slide 16: Intermediate Commissioning Phase
After full transmission is reliably achieved beam-based methods for system commission are available. All subsystems, which require beam, are commissioned and calibrated in this phase.
Beam quality is optimised to initial beam performance parameters.
Goal: Slice Emittance reproducible below 1mm mrad at 0.5nC
Requirements: Transmission, stable, and reliable operation

## Slide 17: Intermediate Commissioning Sequence
Beam based Commissioning (standard and special diagnostics / LLRF)
Gun beam based alignment (laser position, solenoid position)
ACC1/39 combined operation
Slow feedbacks (Orbit, RF, …)
(semi-parasitic-)emittance measurement and optics matching
Transverse deflecting structure (TDS)
Studies and optimisations of the transverse and longitudinal phase spaces
Laser heater undulator closed but without laser (optics distortions)

## Slide 18: Operation Procedures and Tools
Automatic orbit steering
  Manual orbit correction does not scale to large XFEL
  Beam-on-demand mode to mitigate losses
Autophasing
  Set Linac Modules on-crest with LLRF
  and fine automated Spectrometer / BAM scans

## Slide 19: Phase Space Measurements
Beam moments are determined at a reference point using beam size measurements at different points in the machine or for different quadrupole settings
optics is adjusted to match the design using upstream matching quads
Matching iterations
Reliable and efficient measurements are essential for beam optics setup and beam quality optimisation
Tomographic reconstruction of the phase space is also possible
measured beam size
calculated beam size
Initial beam moments
screen
quadrupole
reference point
matching quads

## Slide 20: Phase Space Diagnostics
Semi-parasitic due to fast kickers and off axis screens
Screen 2
Screen 1
Screen 4
Kicker
Kicker
Kicker
Kicker
OTR
Christopher Gerth
WP-18 Special Diagnostics
OTR
Visualisation of beam moment fit
Beam size measurements represented by coloured lines

## Slide 21: Phase Space Diagnostics
Semi-parasitic due to fast kickers and off axis screens
Time resolved (slice-) emittance with a transverse deflecting structure
Requires commissioning of:
  Fast kickers
  Screen systems
  Orbit feedback systems
  TDS RF/LLRF systems
  Data processing and analysis
Screen 2
Screen 1
Screen 4
Kicker
TDS
Kicker
Kicker
Kicker
OTR
Christopher Gerth
WP-18 Special Diagnostics

## Slide 22: Summary
Sequential approach with intermediate milestones
Most milestones can be reached with reduced gun performance (but not with reduced gun availability)
Start with reduced repetition rate but full pulse length
Hardware component commissioning
Beam dynamics setup
Controls Software and operation procedures consolidation

## Slide 23
  Thank You for Your Attention!

## Slide 24: Injector Commissioning Schedule
24

## Slide 25: Final Commissioning Phase
Extension of intermediate commissioning phase goals toward the full range of possible bunch charges and train configurations to full specified train length.
Full Injector Performance (all TDR working points)
Reliable procedures for working point change
Laser Heater characterization

## Slide 26: Laser Heater
Two commissioning stages:
  Undulator closed in intermediate commissioning phase
    Optics
    Magnet handling and control
  Laser operation in final phase
    trans. and long. overlap
    energy spread vs. laser power
    long. phase space TDS
Mathias Hamberg, Volker Ziemann, Uppsala University

## Slide 27: Laser Heater Optics

## Slide 28: Laser Heater
Two commissioning stages:
  Undulator closed in intermediate commissioning phase
    Optics
    Magnet handling and control
  Laser operation in final phase
    trans. and long. overlap
    energy spread vs. laser power
    long. phase space TDS
Mathias Hamberg, Volker Ziemann, Uppsala University

## Slide 29: Laser Heater Spectrum
Simone Spampanati et. al., Proceedings of FEL2012, Nara, Japan
LH simulations by Martin Dohlus
electrons (sigma)
laser beam

## Slide 30: High Level Controls Software
Controls software is essential for reliable machine operation and commissioning
Preparation is work in progress in different groups
“VirtualXFEL” test environment with simulated data
  test of the foreseen architecture in it's whole (e.g. interfaces, scaleability, performance, …)
  test of physics applications (like e.g. Optics Server, Bump Tool, Orbit feedbacks, …)
Synergies with FLASH

## Slide 31: Laser Heater
Two commissioning stages:
  Undulator closed in intermediate commissioning phase
    Optics
    Magnet handling and control
Mathias Hamberg, Volker Ziemann, Uppsala University