## Milestones
Preface: The timely tunnel closure on 30.06.2016 requires a more aggressive schedule than just 1 module per week or one RF string per month. Therefore a learning curve is assumed here with an increased rate of module production and testing and a shorter installation time reachin a factor 1.5 by cryo string 6. This still requires parallel work on cryo strings and RF units and an even higher speed or steeper learning curve for the work on the RF and electronics.
| Milestone Name | Date | Explanation
1 | Modules String 1 ready from AMTF | 2014-10-02 | Modules completely tested, waveguides equipped, all auxiliaries complete, ready for tunnel
2 | Modules String 2 ready from AMTF | 2015-01-30 | Modules completely tested, waveguides equipped, all auxiliaries complete, ready for tunnel
3 | Modules String 3 ready from AMTF | 2015-04-24 | Modules completely tested, waveguides equipped, all auxiliaries complete, ready for tunnel
4 | Modules String 4 ready from AMTF | 2015-07-10 | Modules completely tested, waveguides equipped, all auxiliaries complete, ready for tunnel
5 | Modules String 5 ready from AMTF | 2015-09-11 | Modules completely tested, waveguides equipped, all auxiliaries complete, ready for tunnel
6 | Modules String 6 ready from AMTF | 2015-11-13 | Modules completely tested, waveguides equipped, all auxiliaries complete, ready for tunnel
7 | Modules String 7 ready from AMTF | 2016-01-12 | Modules completely tested, waveguides equipped, all auxiliaries complete, ready for tunnel
8 | Modules String 8 ready from AMTF | 2016-03-12 | Modules completely tested, waveguides equipped, all auxiliaries complete, ready for tunnel
9 | Modules String 9 ready from AMTF | 2016-05-11 | Modules completely tested, waveguides equipped, all auxiliaries complete, ready for tunnel
10 | Cryo Caps L1 ready | 2014-10-31 | Feed/End Cap connected to ceiling frame, ready for welding
11 | Cryo Caps L2 ready | 2015-03-31 | Feed/End Cap connected to ceiling frame, ready for welding
12 | Feed Cap L3 ready | 2014-12-31 | Feed/End Cap connected to ceiling frame, ready for welding
13 | Cryo Boxes CS3 ready | 2015-01-31 | SCB connected to ceiling frame, ready for welding
14 | Cryo Boxes CS4, CS5, CS6 ready | 2015-06-16 | SCB connected to ceiling frame, ready for welding
15 | Cryo Boxes CS7, CS8, CS9 ready | 2015-12-21 | SCB/End Cap connected to ceiling frame, ready for welding
16 | Cryostring 1 closed | 2014-11-30 | All process lines welded, tested and certified, beam vacuum closed and leak tight, iso-vac ready for pump-down
17 | Cryostring 3 closed | 2015-03-31 | All process lines welded, tested and certified, beam vacuum closed and leak tight, iso-vac ready for pump-down
18 | Cryostring 2 closed | 2015-06-16 | All process lines welded, tested and certified, beam vacuum closed and leak tight, iso-vac ready for pump-down
19 | Cryostring 4 closed | 2015-08-25 | All process lines welded, tested and certified, beam vacuum closed and leak tight, iso-vac ready for pump-down
20 | Cryostring 5 closed | 2015-10-27 | All process lines welded, tested and certified, beam vacuum closed and leak tight, iso-vac ready for pump-down
21 | Cryostring 6 closed | 2015-12-22 | All process lines welded, tested and certified, beam vacuum closed and leak tight, iso-vac ready for pump-down
22 | Cryostring 7 closed | 2016-02-16 | All process lines welded, tested and certified, beam vacuum closed and leak tight, iso-vac ready for pump-down
23 | Cryostring 8 closed | 2016-04-12 | All process lines welded, tested and certified, beam vacuum closed and leak tight, iso-vac ready for pump-down
24 | Cryostring 9 closed | 2016-06-07 | All process lines welded, tested and certified, beam vacuum closed and leak tight, iso-vac ready for pump-down
25 | RF station A2 ready | 2015-01-23 | RF station ready for operation on absorber
26 | L1 ready for warm commissioning | 2015-02-20 | RF station, LLRF, technical interlock, personnel interlock, control system, shielding and auxiliaries ready for warm operation of modules
27 | Last RF station ready | 2016-06-30 | RF station ready for operation on absorber
28 | Module for Injector ready | 2015-05-15 | Module completely tested, waveguides equipped, all auxiliaries complete, ready for tunnel
29 | 3rd harmonic module ready | 2015-05-15 | Module ready for tunnel
30 | Injector String closed | 2015-06-15 | All process lines welded, tested, beam vacuum closed and leak tight, iso-vac ready for pump-down
Formulas:
Date = [Date, row above]+84