## Slide 1: Installation Status
Markus Hüning
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: Linac Section Installation
XFEL ACB – April 22, 2015
Hans Weise, DESY

## Slide 3: L1 in Operation

## Slide 4: Cabling of the L1 Linac Section

## Slide 5: L1 in Operation
Since Monday, April 20th L1 can officially be operated
New access rules had to be implemented (XTL is now accelerator)
Finalize installation of electronis
Need to share time between installation and commissioning
  This week: cabling; next week: RF operation

## Slide 6: Schritt 5: Betrieb der Module

## Slide 7: Constricted Room

## Slide 8: L3 Installation

## Slide 9: Installation Sequence
1 Woche / Modul
8 Wochen / Kryostring

## Slide 10: Less Crossings between Welding and Transport
Last String, that can be operated up to now

## Slide 11: Sub-Distribution for L3 awaiting Installation

## Slide 12: Cabling work
Magnet cables pulled whenever injector schedule and L1 commissioning allows
RF reference lines for L3

## Slide 13: String Connection Boxes
Statics of suspension frames finally OK
Due to manufacturing error frames need to be straightened
Acceptance test of first SCB starting next week, then two more bi-weekly

## Slide 14: Injector Installation

## Slide 15: Injector Installation
Currently Gun in Operation
  First Beam!
Starting May 11th shutdown to install module A1 and finish warm section of injector
Short operation period starting June 30th
As soon as AH1 (3.9 GHz module) is ready interrupt for completion of injector linac

## Slide 16: BC1

## Slide 18: Girder Production

## Slide 19: Bunch Compressors
21 girders in BC1 and BC2
  7 finished so far
50 concrete columns
24 racks and 2 modulators/klystrons

## Slide 20: XTD2

## Slide 21: XTD2 Installation
Undulator Supports and Iinfrastructure ready
Photon Beamlines well advanced (see A. Schwarz)
Electron Beamline supports ready
Waiting for Support Beams for Undulator Vacuum Chamber

## Slide 22: Beam Line Suspension

## Slide 23: End of L3, CL, TL
70 magnet suspension frames, 66 to be manufactured, 4 in house
  Very massive to reduce vibrations
~400 m of vacuum line + vacuum suspension
At the end of XTL 3 beamlines above or besides each other

## Slide 24: „Base“ of Vacuum Suspension

## Slide 25: Welded Fixtures for Suspension Frames

## Slide 26: Frames already in house

## Slide 27: General Remarks
Like in the cold linac so far everything is driven by availability of components
  Installation schedules kept shifting
  Variety of reasons, some within WPs some outside
This resulted in a period of very little activity in XTL (and XTD2 to a lesser extend)
  This must come to an end if we are to keep the project schedule goal