## Slide 1: Agenda of XFEL Collaboration Meeting
Short status on module assembly O. Napoly
Cavity performance degradation ON + discussions
Cavity degradation during string assembly S. Berry + discussions
Enhanced Quality Control on module assembly T. Trublet + discussions
Non-conformities of incoming components ON-TT + discussions
Integration problems for CPI couplers discussions
Issue on BQU A. Matheisen
Missing parts until XM100 discussions

## Slide 2: Status of String and Module Assembly
XFEL cryomodule integration at CEA/Saclay

## Slide 3: Outline
Achievements:
  Recent developments
  Production and schedule
  Challenges
  Module performance
  Module repair
  Risks

## Slide 4: Organisation of Work Stations
The breakdown of the assembly work of 7 Work Stations aims at:
balancing almost equally the time occupancy of each WS,
bringing the largest occupancy below 5 days
Clean Room Cold Coupler Area (IS04-CC-WS1)
  Cold coupler assembly (x8)
  Leak check of caity-coupler connection (+RGA)
Clean Room String Assembly Area (ISO4-SA-WS1, ISO4-SA-WS2)
  String connections (1 gate valve + 8 cavities + 1 Qpole unit)
  Leak check of string and N2 venting (+RGA)
Roll-out Area (RO-WS1, RO-WS2)
  HOM adjustment, magnetic shielding, T-sensors (x6)
  Tuner assembly (x8), coupler 4K and 80 K shields
  2 Ph-tube welding, NCT (LT, PT, RT)
  Cold-mass/string connection
Alignment Area (AL-WS1, AL-WS2)
  Cavity and quadrupole fine alignment (~100 µm)
  Welding of 8 mm LHe filling line (x9)
  Tuner and piezo electric tests
Cantilever Area (CA-WS1)
  Welding of 4K and 70 K shields, 4K and 79 K super insulation
  Cable routing and insulation, Quad current lead
  Insertion into vacuum vessel and cold mass alignment
Coupler Area (CO-WS1, CO-WS2)
  Warm couplers + coupler pumping line + leak checks (8 connections + coupler vacuum)
  Cabling of flanges A (x8) and flange D
  Quadrupole current lead connections and welding
  Final leak check of cavity vacuum + final pumping
Shipment Area (SH-WS1, SH-WS2)
  Control operations (RF frequency)
  End-caps closing, N2-insulation
  CEA-Alsyom “acceptance test”
  Loading

## Slide 5
Assembly Procedures

## Slide 6
Assembly Procedures

## Slide 7
Assembly Procedures

## Slide 8
Assembly Procedures
The preparation, assembly and control work are described in 179 procedures, ‘Fiches d’Instruction’, ‘used’ by the operators.
The first set of draft procedures was written by CEA, during the Prototyping phase at DESY and Saclay, in English and appended to the Call for Tender Specifications for Industrial Operator selection
Alsyom, the selected Industrial Operator, was in charge of updating these procedures during the Pre-Series phase (3 modules) and to translate them in French for their usage during the Series production phase.
This took much (much) longer than expected ! 166 are final.

## Slide 9: Integration Tools
Socks used to transfer cavity string from Clean Room to Roll-out Area, suppress time-consuming cleaning of cavity posts
Productivity may still gain from improvement of small tools

## Slide 10: Integration Tools
Transfer carriages for cold coupler pairs and coupling box
Productivity may still gain from improvement of small tools

## Slide 11: Integration Tools
Two more examples, in use:
1) Pre-fabricated et reusable devices for the leak-check of
the cavity string connections  3 units fabricated and in use.
Inter-cavity connection leak-check box, including cold coupler connection, and pre-existing HOM flanges
2) Realization of gate valve support for its assembly on Cold-Coupler workstation:
Design and fabrication taken over by Alsyom, used for XM22.

## Slide 12: Throughput at Cold Coupler WS
12

## Slide 13
13
Throughput at String Assembly WS

## Slide 14
14
Throughput at Roll-out WS

## Slide 15
15
Throughput at Alignment WS

## Slide 16
16
Throughput at Cantilever WS

## Slide 17
17
Throughput at Warm Coupler WS

## Slide 18: Cryomodule Asssembly Time
18
7 weeks = 7 x 5 working days was reached mid-October 2014 with XM15
 the design of the Assembly Infrastructure was sound
7 x 4 working days was reached on 5 January 2015 with XM25
This accelerated production is needed to close the XFEL tunnel mid-2016

## Slide 19: Alsyom to CEA Cryomodule Delivery
19

## Slide 20: CEA to DESY Cryomodule Delivery
20
Shipment Rate to DESY / week
mid-October 2014
January 2015
As of April 22, 2015: 45 out of 103 modules shipped to DESY.
Throughput of 4 days started in 2015 : from January 5 till April 21, CEA delivered 18 cryomodules (XM25 to XM42) in 69 working days (69/4=17,25).
If we maintain the 4 day throughput (so-called acceleration of production) XM100 will be delivered around 20 April 2016.
The accelerated scheme is robust: it has already absorbed major incidents.
1
2
3
4
21 April 2015

## Slide 21: Quality Control
Quality Control consists in:
Inspecting the incoming components
Controling the assembly work in person
Documenting the controls and non-conformities
Until end of 2014, the quality control group of Alsyom was too small (3 people) in such a way that Documenting and Incoming Inspection was performed in priority. CEA took the major part of the Assembly Work Controling, essentially during pre-defined ‘Hold Points’.
The ‘every day’ or ‘random’ controls were too few and this led to many mal-fabrication, most of them recorded at DESY before or during cryomodule cold test !
In November 2014, the quality control group of Alsyom was increased to 5 people which, together with the better organisation, covers the need of QC.

## Slide 22: Quality Control: Non Conformities
Non Conformities recorded by Alsyom fall into 3 categories:
Tooling and assembly equipment, from CEA and DESY (pump stations) (TOOLING)
Accelerator components (PRODUCT)
Assembly operation (PROCESS)

## Slide 23: Quality Control: Non Conformities
The number of Non Conformities is NOT going down.
But, with better and more efficient detection at Incoming Inspection, the impact of PRODUCT NC on the module assembly has considerably decreased, compared to when many NC were discovered ‘on the fly’.

## Slide 24: Cryomodule Performance
All tested modules are on XFEL specs (188 MV per module), on average 15 % above specs (27.2 MV/m).
Some very important cavity gradient degradation have been recorded: XM-3 and XM30 are the two exceptions.
Individual cavities are power limited to 31 MV/m, i.e. cryomodules to 250 MV.

## Slide 25: Cryomodule Performance : XM-3

## Slide 26: Cryomodule Performance : XM19

## Slide 27: Cryomodule Performance : XM19

## Slide 28: Cryomodule Performance : XM30

## Slide 29: About Cavity Degradation
CEA and DESY are working on understanding the causes of cavity degradation after module assembly.
1st remark: one module is worth > 1 M€ and 200 MV. We lost about ¼ M€ on XM12 and ½ M€ on XM20. This cost is worth investing in in-situ (AMTF) diagnostic and in-situ repair (better conditioning).
2nd remark: about 80% of cavities are reproducing or improving their VT performances: module integration is based on a sound process. Causes ?
3rd remark: a smaller but significant number of cavities improve their gradient after module integration.
Individual cavities are power limited to 31 MV/m, i.e. cryomodules to 250 MV.

## Slide 30: About Cavity Degradation
The gradient degradation is presumably du to contamination of the cavity RF surfaces. Contamination can occur by two processes:
External contamination of cavity volume
Internal contamination of cavity volume
1st process: External contamination may have 3 causes:
a) Clean room air: idle ISO5-ISO4 clean rooms are worth ‘ISO0’: permanent counting at nights monitors cleanliness
b) Operator behavior : hands-on cavity connections and bad preparation work is a highly probable cause of contamination. DESY and CEA performed two audits of clean room assembly. No major faults were detected but some procedures needed a reminder. Also, the connection of the gate valve to cavity is difficult, particularly on the CC workstation.
c) N2 Flushing (10 l/mn) and N2 venting (3 l/mn): venting systems release 10k particulates / mn in open air, but in-cavity tests measured less than 10 particulates / mn on realistic conditions of cavity venting. Systematics ??

## Slide 31: About Cavity Degradation
2nd process: Internal contamination may have 3 causes:
Particulates migration: metallic particulates are inevitably present or produced in the RF-free volumes around flanges. The ‘art’ is not to move them using controled slow venting and slow pumping, and avoiding vibration. Flushing with clean N2 is questionable from this point of view.
Vibrations: ‘Sticking’ theory predicts that particulates stick to the surface when cavity is under vacuum  cavity and cryomodule transports are done under vacuum. Vibrations are recorded: the case of XM19 and XM26 cavities (not an isolated case)
XM26 cavities have been shipped back to DESY and tested a second time in VTC
XM19 cavity transport > 3g
after 2nd transport

## Slide 32: About Cavity Degradation
2nd process: Internal contamination may have 3 causes:
Vibrations: vibrations occurs alos during the ‘5 assembly weeks’ outside of the clean room when the string is vented.
e.g vibrations during cut-out of Ti tubes e.g hammering of 6 pins
of the 2K 2-phase line along cavities on cold mass
The maximum acceptable acceleration
levels remains unknown to us.
XM35: 0.7 g during cutting for 2 mn, up to 4g shocks
during cutting tool positioning.

## Slide 33: About Cavity Degradation
2nd process: Internal contamination may have 2 causes:
b) Particulates creation and migration: copper coating flakes on intercavity bellows and coupler Cold External Conductor are particularly suspected.
Conclusions:
several suspects were interrogated but the culprit is still loose  
ILC could help in conducting some assembly and RF tests.