## Slide 1: Optical Laser Installation at SASE 1
Hamburg, 24th April, 2015
Max Lederer, Laser Group, WP78, European XFEL
max.lederer@xfel.eu
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: Overview
  Laser Group WP78
  Pump-probe laser R&D status
  SASE 1 pump-probe laser installation
  Conclusion

## Slide 3
Laser group at European XFEL GmbH
Foundation: project WP-78, November 2010
Mission:
Provide and operate laser equipment for the x-ray beam line experiments
In-house developments
Industrial and academic collaborations
Personnel:
  Construction
  phase: 10
  Installation,
  commissioning,
  operation: 13+

## Slide 4
Laser group at European XFEL GmbH
Misha Pergament (pp-laser)
Martin Kellert (pp-laser)
Jin Wang (pp-laser)
Kai Kruse (pp-laser)
Guido Palmer (pp-laser and instruments interface)
Gerd Priebe (HED-lasers, HIBEF)
Ulrike Wegner (pp-laser)
Max Lederer
(group leader)
Laurens Wißmann (mon. and contr.)
Moritz Emons
(pp-laser and instruments interface)

## Slide 5
Laser Advisory Committee (LAC)
Joint European XFEL and DESY LAC:
  Review, evaluate and expertly advise laser groups on all developments, installations and operations of facility related lasers
  Provide strategic advice to management and report to SAC
  Members
    Uwe Morgner (LZH, Uni Hannover), Chair
    Giulio Cerullo (Politechnico di Milano)
    Patrick Georges (Institut d’Optique, Paris)
    Alfred Leitensdorfer (Uni Konstanz)
    Robert Schoenlein (LBNL, Berkeley)
    William White (SLAC)
    Mike Dunne (LCLS)
LAC convened the 4th time in September 2014, endorsing our efforts and progress.

## Slide 6
PP-Laser R&D status

## Slide 7: European X-ray Free Electron Laser Facility
3 underground experimental areas with 3 X-ray beams
6 experiment stations
Up to 60% of experiments require optical lasers.

## Slide 8: European XFEL experimental laser plans
SQS
SCS
SPB
FXE
HED
Types of experimental lasers:
PP (pump-probe):
  sub-15…100fs, 0.2mJ, 10Hz burst, 0…4.5MHz, 800nm
MAL (molecular alignment):
  sub-20fs, 3…10mJ, 10Hz burst, 800nm („kick“)
  or
  1J-class, 10Hz or burst, ns („adiabatic“)
TUNE (tuning, freq. conversion):
  UV…mid-IR, THz
TW (Terawatt):
  <30fs, >1Hz, 100 Terawatt–class laser, Ti:sapphire
SHOCK (high energy):
  100J … kJ-class ns-laser, exponential ramp
Baseline
HiBEF User Consortium
SASE 3
SASE 1
U2
U1
SASE 2
Experiment Hall
MID
PP
TW
TUNE
MAL
SHOCK
PP
TUNE
MAL
PP
TUNE
PP-type
high rep-rate
HE/HI-type
PP
MAL
PP
TUNE
MAL
PP
TUNE
Notes: Before you start editing the slides of your talk change to the Master Slide view: Menu button “View”, Master, Slide Master:
Edit the following 2 items in the 1st slide: 1) 1st row in the violet header: Delete the existent text and write the title of your talk into this text field 2) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area Close Master View

## Slide 9
Status of pump-probe laser NOPA R&D
Some features:
180µJ per pulse, 34W average power during burst
Nearly transform limited pulses: 15fs … 75fs
100nm tuning for longer pulses
200kHz and 4.5MHz intra-burst operation
Identical performance from BBO and LBO
15fs
600µs burst
Arb. sequence
diff. lim.
High power burst-mode optical parametric amplifier with arbitrary pulse selection
Optics Express, Vol. 22, Issue 18, pp. 22202-22210 (2014)

## Slide 10
What‘s left to do?
  Finalize till Q1 2016:
      5kW-pumped NOPA-stages
      Control and monitoring integration of PP-laser (Karabo etc.)
      PP-laser layout and CAD-integration
      Some opto-mechaical desings, environmental stability
      Procurement
      Evaluation of 20kW pump
All efforts are currently on track.

## Slide 11
SASE 1 Pump-Probe Laser Installation

## Slide 12: Status November 2014
  WBS-document for SASE 1 completed
    Identified stake holders and their function as: „coordinator“, „executor“, „customer“
    Identified 5 phases with associated tasks:
      Before installation of laser tables (Start hutch construction -> Mar. 2016)
      Installation of laser tables and additional (under-table) infrastructure (Apr. -> June 2016)
      Installation and commissioning of laser components in PP-Hutch (Jul. 2016 -> Apr. 2017)
      Final Commissioning of AC (Dec. 2016)
      Beam delivery to ILH and experiment (Jul. 2016 -> Apr. 2017)
    Handed over to PSPO

## Slide 13
WBS SASE 1: major tasks and responsibilities

## Slide 14
WBS SASE 1: major tasks and time line
  Detailed planning of phase III is currently being drafted
NOW

## Slide 15: I: Before installation of laser tables (-> Mar. 2016)
          At the end of phase I we have:
          Electricity, network, water, gas as specified at walls
          Electricity, network, water at access point for under-table installation
          AC and GR condition
          Ideally:
              Hutch access control
              Safety (general and laser)
              Sync-cable (WP-18)
Access point for
under-table installation

## Slide 16: II: Installation of laser tables and additional (under-table) infrastructure (Apr. -> Jun. 2016)
          At the end of phase II we have:
          Laser tables and furniture installed
          Under-table installation complete as specified
          Beam delivery pipes installed
          Climate separation
          Hutch access control
          Safety (general and laser)
          Sync-cable (WP-18)
          AC initial comm. and CR conds.
          Furniture
Access point for
under-table installation
DT=21+/-0.1°C
DT=21+/-1°C

## Slide 17: III and IV: Installation and commissioning of laser components in PP-Hutch (Jul. 2016 -> Apr. 2017)
          At the end of phase III we have:
          Operative PP-laser with synchronization and Karabo-control
          Beam delivered to ILH
          Exclusive WP-78 effort
Access point for
under-table installation
          Phase IV:
          Fully commissioned AC

## Slide 18: V: Beam delivery to ILH and experiment (Jul. 2016 -> Apr. 2017)
          At the end of phase V we have:
          Beam delivered to first experiment
          Combined effort WP-81/84 and WP-78

## Slide 19
Conclusion
  Laser installation at SASE 1
  PP-laser development status: on schedule
  PP-laser procurement started mid 2014: ongoing
  Installation planning: WBS with time line
  PP-laser hutch planning: finalized
  Hutch construction: masonry started

## Slide 20
Thank you!!

## Slide 21
SASE 1 laser hutch constr. status