## Slide 1: Installation Schedule
Markus Hüning
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: Warm Beamlines in XTL
900 lattice elements
385 magnets, 234 main magnets, 98 on girders
Approx. 1100m of beam line
Partly (B0, B1, B2) to be installed under clean room conditions
The downstream parts to be suspended from the ceiling

## Slide 3: General Remarks
Like in the cold linac so far everything is driven by availability of components
  Installation schedules kept shifting
  Variety of reasons, some within WPs some outside
This resulted in a period of very little activity in XTL
  This must come to an end if we are to keep the project schedule goal

## Slide 4: Scheduling
Installation of bunch compressor bypass lines progresses
  completion expected before summer
Large scale production of components just started
  Very soon – or in this meeting respectively – will have a clearer picture of delivery times
It is now time to reestablish the schedule
In this talk I can give only a rough outline

## Slide 5: Bunch Compressors
21 girders in BC1 and BC2
  7 finished so far
50 concrete columns
24 racks and 2 modulators/klystrons

## Slide 6: BC1

## Slide 8: BC1

## Slide 10: Cabling work
Magnet cables pulled whenever injector schedule and L1 commissioning allows
RF reference lines for L3

## Slide 11: Sequence
Vacuum Connections
Concrete Pillars&Girders
Cryo Transfer Line
Finish
Concrete Pillars&Girders
Cryo Transfer Line
Cables and Electronics
Summer time
B1
B2
Vacuum Connections

## Slide 12: End of L3, CL, TL
70 magnet suspension frames, 66 to be manufactured, 4 in house
  Very massive to reduce vibrations
~400 m of vacuum line + vacuum suspension
At the end of XTL 3 beamlines above or besides each other

## Slide 13: Beam Line Suspension

## Slide 14: „Base“ of Vacuum Suspension

## Slide 15: Welded Fixtures for Suspension Frames

## Slide 16: Frames already in house

## Slide 17: Sequence
Finish
Cables and Electronics
Summer time
Install Suspension Frames & Magnets
Install Vacuum Components
Manufacture Suspension Frames
Manufacture Vacuum Components

## Slide 18: Sequence
Christmas
Summer time
Finish
Vacuum Connections
Concrete Pillars&Girders
Cryo Transfer Line
Concrete Pillars&Girders
Cryo Transfer Line
Cables and Electronics
B1
B2
Vacuum Connections
Cables and Electronics
Install Suspension Frames & Magnets
Install Vacuum Components
Manufacture Suspension Frames
Manufacture Vacuum Components

## Slide 19: Closing Remarks
Start of B1 installation presumably fits with end of injector shutdown
Does machine installation in XTD2 finish before end of summer?
Can we release manpower early to help out elsewhere?