## Slide 1: Status of downstream L3 (R28-R40) vacuum (WP19)
presented by S. Lederer
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: Overview
5 different beam lines:
L3 (145 m) – warm beam line downstream of the last accelerating module
  Beam line design and fabrication of beam pipes, supports, bellow units and pump-crosses by BINP
  Valves, pumps, fast shutters, cables and control system by DESY
    RF-inserts and fiducial plates for In-line SIPs by BINP
Collimation section (200 m)
  Beam line design and fabrication of beam pipes and supports by DESY
  Main collimators and bellow units by BINP
  Valves, pumps, fast shutters, cables and control system by DESY
    RF-inserts and fiducial plates for In-line SIPs by BINP

## Slide 3: Overview
Switch yard (170 m):
  Beam line design and fabrication of beam pipes and supports by DESY
  Valves, pumps, cables and control system by DESY
    RF-inserts and fiducial plates for In-line SIPs by BINP
  DN50 bellow units by BINP
TLD beam line (140 m, including XS1)
  Beam line design and fabrication of beam pipes and supports by DESY
  Valves, pumps, cables and control system by DESY
    RF-inserts and fiducial plates for In-line SIPs by BINP
  DN50 bellow units by BINP

## Slide 4: Overview
T1 beam line (100 m in XTL):
  Beam line design and fabrication of beam pipes, supports, bellow units and pump-crosses by BINP
  Valves, pumps, fast shutters, cables and control system by DESY
    RF-inserts and fiducial plates for In-line SIPs by BINP
T2 beam line (30 m in XTL)
  Beam line design and fabrication of beam pipes, supports, bellow units and pump-crosses by BINP
  Valves, pumps, fast shutters, cables and control system by DESY
    RF-inserts and fiducial plates for In-line SIPs by BINP

## Slide 5: Status
Beam line reviews took much longer as expected
  Its obviously impossible to get an reliable 3d model from the CAD integration process
  Changed from standing to hanging beam lines yielded a delay of over one year
Finally the clearance for production was coupled to the “Steuerskizze” (automatic placement of components depending on the lattice file)

## Slide 6
Most challenging installations, where the three beam lines (T1, T2 and TLD) go “parallel”
e-
T1
T2
TLD

## Slide 7
With supports things don’t look easier

## Slide 8: Status - Rough number of components
Components | DESY | BINP | 
Standard SIPs | 50 | 0 but auxiliary parts needed | 
In-line SIPs | 110 | 0 but auxiliary parts needed | 
Gate valves | 10 | 0 | 
DN50 beam pipes | 150 | 60 | 
DN50 bellow units | 0 | 180 | 
Main collimators | 0 | 4 | 
Septa | 2 | 0 | 
Of course for all components supports are required
* (green mean in-house)

## Slide 9: Status
Fabrication of beam lines Collimation, Switch yard and TLD started – scheduled RFI 09/2015
Fabrication of L3, T1 and T2 beam lines to be started now to have them RFI 09/2015
Valves and pumps for all beam lines are available
  Preparation work for in-line pumps (installation of RF-inserts, installation of plates for fiducials) depend on BNIP delivery – delayed from 03/2015 to 09/2015 w/o any given reason
Installation of Rose+Krieger supports started by WP33

## Slide 10: Final remarks
Discussions on beam line installation started and will go on (WP19/WP33/WP34)
Installation of cables (not done by WP19) could be critical – has to be integrated in installation planning
Documentation of the machine is not defined at all up to now
  EDMS business of the sections or even girders unclear
  Pending issue of installation drawings – has to be solved centrally and not on the shoulders of WPs in principle not responsible for CAD integration
    Despite the documentation issue it is also required for installation
    THIS HAS TO BE SOLVED!