## Slide 1: X-ray Photon Diagnostics Status 23 April 2015
Jan Grünert / WP74
(Grünert, Baranasic, Buck, Dietrich, Freund, Koch, Kujala, Liu, Lübbe, Planas)
European XFEL GmbH, Hamburg
4th XFEL Collaboration Meeting

## Slide 2: Status WP74
Commercial production: Pop-in monitors, HiREX
In-house production at European XFEL: 2D-imager-FEL, K-Mono, PES, Diff.Pumps
Production by DESY: XGM, transmissive imager
Production by Dubna: MCP-based detector
Design stage: 2D-imager-SR, Exit Slit Imager, Timing Diagnostics
Perspectives until fall 2015:
  Installation of vacuum chambers in XTD2
  Installations in XTD9 (depending on tunnel status)
  Production of most SASE3 / XTD10 devices
  Finalizing designs for HiREX and Exit Slit Imager
  Production of first 2D-imager-SR
  More diagnostics activities (see summary)

## Slide 3: WP74 devices in XTD2 (SASE1)
All z-distances given in the PD coordinate system
619.0m: Filter chamber
620.6m: Transmissive Imager (=OTR-C screen)
639.5m: K-monochromator system, incl. 2D-imager-SR
648.9m: X-ray gas monitor (XGM)
655.9m: Differential Pumping by WP74
659.2m: Photoelectron spectrometer (PES)
681.8m: 2D-imager-FEL
698.9m: MCP detector
700.4m: Pop-in Monitor Type II-45°

## Slide 4: Filter chamber
N:\4all\intern\User data\wp74\Devices\31-2_K-Mono\production drawings\filter chamber
Status 04/2015: assembly finished, final RGA tests
Alignment base plates done
Will now be transferred to WP19 (warm vacuum ) for installation

## Slide 5: Transmissive Imager
N:\4all\intern\User data\wp74\Devices\31-8_Transmissive-Imager
„OTR-C“ imager = a standard WP17 device
  (only internal modification for scintillator/holder by WP74, which was done in contact with WP17)
Integration by WP17 as for their other screen stations
Modified scintillator holder was produced

## Slide 6: K-Monochromator
N:\4all\intern\User data\wp74\Devices\31-2_K-Mono
Status 4/2015: DR/PRR done, prototype was converted into SASE1 device
Final assembly done, now RGA tests; Installation in XTD2 this month
Chambers for SASE2+3 arrived, assembly SASE3 K-mono starts 5/2015
Control crate available and tested

## Slide 7: X-ray Gas Monitor (XGM)
N:\4all\intern\User data\wp74\Devices\11-1_XGMD\Drawings\FEM steel base frame\support_pillar_pictures
Status 04/2015:
Two XGMs are RFI, four more are in production (Tiedtke group @ FLASH)
Transport / Installation in XTD2/SASE1: 6.May 2015
Installation in XTD9/SASE1: when tunnel is ready (temp.storage at HERA-S lab)
4 remaining XGMs will be RFI at end of 07/2015
Supports: installed in XTD2 in 5/2014
and next week in XTD9

## Slide 8: 2 XGMs are RFI at FLASH2 hall

## Slide 9: Differential Pumping by WP74 (between PES and XGM)
N:\4all\intern\User data\wp74\Devices\11-1_XGMD\Drawings\FEM steel base frame\support_pillar_pictures
Status 04/2015:
Design done, mostly standard parts, simlar to WP73 systems
All vacuum components arrived except pumps (>3M delay)
May 2015: Test setup of one system for optimization in HERA-S hall
Tunnel installation will be together with the PES (first in SASE3 in Q4/2015)

## Slide 10: Photoelectron spectrometer (PES)
N:\4all\intern\User data\wp74\Devices\11-1_XGMD\Drawings\FEM steel base frame\support_pillar_pictures
Status 04/2015:
Detailed design done for SASE3 device and for the fully motorized support
SASE3 device fully assembled and very successfully tested with X-ray FEL beam (scientific beamtime L52 at AMO/LCLS)
Device returns from SLAC latest 11/2015
SASE1 device will be developed (requires modifications for hard X-ray application)  not available in current XTD2 installation phase  temporary 1.6m long DN40CF pipe + holder

## Slide 11: PES assembly (SASE3 device)

## Slide 12: Transport to SLAC and use at AMO / LCLS

## Slide 13: 2D-imager (FEL)
..
Status 04/2015:
Final assembly of SASE1 device
Installation in XTD2 planned for May/June 2015

## Slide 14: MCP-based detector (by JINR)
N:\4all\intern\User data\wp74\Devices\31-1_MCP-Detector\3D-sketches
Status 04/2015:
Final devices SASE1 + SASE2 are RFI at HERA-S
SASE1 device to be transfered to XHE3
Camera section to come

## Slide 15: Pop-in Monitor Type II-45°
N:\4all\intern\User data\wp74\Devices\31-4_Pop-In-Monitors
Status 04/2015
FDR/PPR/production done (JJ X-ray)
SAT of all devices for all tunnels in 10/2014
Detailed optics implementation approved 03/2015
Final assembly of scintillators and vacuum tests in 3/2015
Device for XTD2 is ok & RFI, will be installed within April 2015

## Slide 16: Imagers
SAT for
Pop-in Monitors
Status SR-Imager in 04/2015:
Detailed optics design: done
Detailed 3D design: done
Workshop drawings: done and submitted to commercial providers
Company for production identified

## Slide 17: 2D-imager-SR (SRimager)

## Slide 18: WP74 summary for SASE1 / XTD2
Filter chamber
Transmissive Imager
K-mono
2D-imager (for SR)
XGM
Differential Pumping by WP74
PES
2D-imager (for FEL)
MCP detector
Pop-in Monitor II-45°
OK
OK
OK
11/2015
OK
OK
temp. solution
OK
OK
OK
Device
RFI status

## Slide 19: Other current WP74 design activities (not related to XTD2 installations)
Hard X-ray High Resolution Single Shot Spectrometer (HXHRSSS, now called HiREX)
  Design Document (physics, simulations)
  Technical Specifications Document finished and reviewed
  Public Tender started (awarding mid-May)
  detailed technical design by company until fall 2015
  for XTD9 / SASE1
new

## Slide 20: Other current WP74 design activities (not related to XTD2 installations)
Diamond Detectors for Intensity & Position Monitoring
Temporal Diagnostics: THz Streaking and Spectral Encoding
Time
Energy
THz streaking
600 fs
Energy
Laser-based THz-generation at XFEL.EU
Prototype chamber for THz-streaking Pulse Length Monitor (TPLM)
Prototype chamber for Photon Arrival time Monitor (PAM)
Development work in 2015:
White-light generation for spectral encoding

## Slide 21: Open issues
Tunnel installation planning needs more details: sequence and dates of device vacuum installations, cabling & other infrastructure, pumped systems in unfinished tunnels, temporary storage in tunnels/shafts,…
Rare gas supply system considerable effort, ~4km of pipes, currently a task within WP74 since excluded from TGA by MKK
Still: Coordination across WPs for common orders
  Control crates (Beckhoff)
  Cables for connecting devices to racks/crates
  …

## Slide 22: WP74 summary
SASE1 / XTD2 devices on track
Other current WP74 design activities:
  Hard X-ray Single Shot Spectrometer
  Diamond Detectors
  Temporal Diagnostics
Need continuously, detailed, coordinated and agreed tunnel installation planning !