## Sheet1
XFEL XTD2 Beamline Review, rooms 11 to 16
WP74 contribution
1 | R11 | transmissive imager (OTRC) support not in contact with girder
2 | R12 / La=2637m | Rack 1.2 seems missing, should be in R12
3 | R12 / La=2636m | The photon beamline component "collimator" is missing in R12
4 | R12 | possible installation sequence collision between K-mono and support pillar for Inline IG Pump
5 | R13 | prevacuum pumps of differential pumping are in the air
6 | R13 | the vicinity of a magnet to the XGM could be problematic. Issue to be clarified (not a CAD collision but operational interference)
7 | R14 / La=2693m (see file XTD2_R13_DG3.jt) | MCP-detector is missing
8 | R14 / La=2694m (see file XTD2_R13_DG3.jt) | Pop-in Monitor is missing
9 | XTD2 R15 and R16 DG3 models | do not contain any WP74 components
10 | XTD2 in general | SLRS and beamlines have an angular and height mismatch. However, tunnel ends and floors match when combining the 3D models of rooms 11 to 16. Since the height mismatch at the SLRS is a non-negligible 66mm, we suspect to find collisions when the SLRS mounts would be actually installed 66mm lower during the construction realization as compared to the model. See figure below.