## Sheet1
Work Package:
Document | Remarks (optional) | Approved | Conditions for approval/reasons for dismissal
XTL_R27 | WP12 not involved | yes | no electro magnets in this CAD room
XTL_R27_DG3 | WP12 not involved | yes
XTL_R27_Interferences | WP12 not involved | yes
XTL_R28 | magnets in DG2 not checked | yes under the condition | Magnets are shown in DG2; not checked
XTL_R28_DG3 |  |  | Collision between support frame and rack next to cryo equipment, electromagnets o.k.
XTL_R28_Interferences | WP12 not involved | yes
XTL_R29 | magnets in DG2 not checked | yes under the condition | Magnets are shown in DG2; not checked
XTL_R29_DG3 |  | yes
XTL_R29_Interferences | WP12 not involved | yes
XTL_R30 | magnets in DG2 not checked | yes under the condition | Magnets are shown in DG2; not checked
XTL_R30_DG3 | WP12 not involved | yes
XTL_R30_Interferences | WP12 not involved | yes
XTL_R31 | magnets in DG2 not checked | yes under the condition | Magnets are shown in DG2; not checked
XTL_R31_DG3 |  | yes under the condition | SA.1674.CL wrong sextupole type; shown XSA0, must be XSA30 according to lattice 8.4.4. XBE-V magnet missing; support is shown.
XTL_R31_Interferences | WP12 not involved | yes
XTL_R32 | magnets in DG2 not checked | yes | Magnets are shown in DG2; not checked
XTL_R32_DG3 |  | yes under the condition | SA.1736.CL, SA.1728.CL, SA.1726.CL,SA.1719.CL, SA.1710.CL, SA.1708.CL, SA.1700.CL, SA.1692.CL, SA.1691.CL, SA.1683.CL wrong sextupole types, shown XSA0 must be XSA30 according to lattice 8.4.4.
XTL_R32_Interferences |  | yes
XTL_R33 | magnets in DG2 not checked | yes | Magnets are shown in DG2; not checked
XTL_R33_DG3 |  |  | SA.1744.CL, SA.1782.CL wrong sextupole types, shown XSA0 must be XSA30 according to lattice 8.4.4.
XTL_R33_Interferences |  | yes
XTL_R34 | magnets in DG2 not checked | yes | Magnets are shown in DG2; not checked
XTL_R34_DG3 |  | yes under the condition | part of vacuum pipe missing; SA.1844.CL, SA.1836.CL, SA.1834.CL, SA.1827.CL, SA.1818.CL, SA.1816.CL, SA.1808.CL, SA.1800.CL, SA.1799.CL, SA.1791.CL wrong sextupole types, shown XSA0 must be XSA30 according to lattice 8.4.4.
XTL_R34_Interferences |  | yes
XTL_R35 | magnets in DG2 not checked | yes | Magnets are shown in DG2; not checked
XTL_R35_DG3 |  |  | vacuum system missing between 1894 and 1892; vacuum system missing between 1884 and 1881; SA.1852.CL wrong sextupole type, shown XSA0 must be XSA30 according to lattice 8.4.4.
XTL_R35_Interferences |  | yes
XTL_R36 | magnets in DG2 not checked | yes | Magnets are shown in DG2; not checked
XTL_R36_DG3 |  | yes | Vacuum Fast kicker missing; parts of vacuum system missing
XTL_R36_Interferences |  | yes
Milestones
Rack Inventory

## Sheet2 (hidden)
yes
yes under the condition
no because of