## Sheet1
Work Package:
Document | Remarks (optional) | Approved | Conditions for approval/reasons for dismissal
XTL_R37 | Magnet DG2 models not checked | yes
XTL_R38 | Magnet DG2 models not checked | yes under the condition
XTL_R39 | Magnet DG2 models not checked | yes under the condition
XTL_R40
XTL_R37_DG3 |  | yes under the condition | TLD: distance between CFY.2000 and CFX.2000 does not match with lattice 8.4.4.
XTL_R38_DG3 |  | yes under the condition | T1: missing vacuum system for the 3 XBZ.
XTL_R39_DG3 |  | yes under the condition | TL: The vacuum holder positioned between the QF.2042 upper/lower clamps is not fixed to ceiling steel frame. The vacuum holder cannot sit within a clamp. If necessary shift holder to the edge of the iron yoke of QF.2042 or position it between the clamps.
XTL_R40_DG3 |  | yes under the condition | T1: Vacuum chamber missing BD.2050 and BD2062; BD.2077 up to BD.2084, BD.2097 up to CFX.2098; Support structure for the magnets are missing between BD.2077 and BD.2084, support structure missing BD.2097, CFY.2093 and CFX.2089. TLD-Beamline: Support structure missing between magnets BV.2087 and SK.2096, magnets CNX.2098 and CNY.2098 are missing.
XTL_R37_Interferences | WP12 not affected. | yes
XTL_R38_Interferences | WP12 not affected. | yes
XTL_R39_Interferences | WP12 (magnets) affected but not mentioned (see XTL_R39_DG3) | yes
XTL_R40_Interferences | WP12 not affected. | yes
Milestones
Rack Inventory

## Sheet2 (hidden)
yes
yes under the condition
no because of