## Sheet1
Work Package: | WP-38
Document | Remarks (optional) | Approved | Conditions for approval/reasons for dismissal
XTL_R27
XTL_R27_DG3
XTL_R27_Interferences | The interferences are due to too large space holders in the model. The installation of all interlock komponents have been or will be agreed in detail with WP of neighbouring components
XTL_R28
XTL_R28_DG3
XTL_R28_Interferences | The interferences are due to too large space holders in the model. The installation of all interlock komponents have been or will be agreed in detail with WP of neighbouring components
XTL_R29
XTL_R29_DG3
XTL_R29_Interferences | The interferences are due to too large space holders in the model. The installation of all interlock komponents have been or will be agreed in detail with WP of neighbouring components
XTL_R30
XTL_R30_DG3
XTL_R30_Interferences | The interferences are due to too large space holders in the model. The installation of all interlock komponents have been or will be agreed in detail with WP of neighbouring components
XTL_R31
XTL_R31_DG3
XTL_R31_Interferences | The interferences are due to too large space holders in the model. The installation of all interlock komponents have been or will be agreed in detail with WP of neighbouring components
XTL_R32
XTL_R32_DG3
XTL_R32_Interferences | The interferences are due to too large space holders in the model. The installation of all interlock komponents have been or will be agreed in detail with WP of neighbouring components
XTL_R33
XTL_R33_DG3
XTL_R33_Interferences | The interferences are due to too large space holders in the model. The installation of all interlock komponents have been or will be agreed in detail with WP of neighbouring components
XTL_R34
XTL_R34_DG3
XTL_R34_Interferences | The interferences are due to too large space holders in the model. The installation of all interlock komponents have been or will be agreed in detail with WP of neighbouring components
XTL_R35
XTL_R35_DG3
XTL_R35_Interferences | The interferences are due to too large space holders in the model. The installation of all interlock komponents have been or will be agreed in detail with WP of neighbouring components
XTL_R36
XTL_R36_DG3
XTL_R36_Interferences | The interferences are due to too large space holders in the model. The installation of all interlock komponents have been or will be agreed in detail with WP of neighbouring components
Milestones
Rack Inventory | no rack space needed.

## Sheet2 (hidden)
yes
yes under the condition
no because of