## Slide 1: PZ16M status and plans
2015 MSK collaboration workshop
Julien Branlard
PZ16M status and plans
ISE, Warsaw, 12.06.2015

## Slide 2: Last slide from last year’s PZ16M presentation
DONE
DONE
PAID
DONE
ON GOING

## Slide 3: WORK DONE IN THE LAST YEAR: meetings…
The PZ16M team
  Marcin Chojnacki
  Marius Grecki
  Konrad Przygoda
  Henning Weddig
  Julien Branlard
  with reviewing help from Michael Fenner

## Slide 4: WORK DONE IN THE LAST YEAR: PEM
Piezo Energy Monitoring (PEM) board

## Slide 5: WORK DONE IN THE LAST YEAR: PEM
Schematic reviewed done
PCB layout (2-3 weeks)
PCB review in July
Production and tests after September
PEM

## Slide 6: WORK DONE IN THE LAST YEAR: main PCB
PZ16M main PCB

## Slide 7: WORK DONE IN THE LAST YEAR: main PCB
Main PCB update
  22 points corrected and reviewed
  Final review pending
  Production of 1-2 prototypes
  Tests
  Revision ?
  Launch call for tender

## Slide 9: WORK DONE IN THE LAST YEAR: firmware
Mariusz Grecki,
Bin Yang,
Lukasz Butkowski,
Julien Branlard

## Slide 10: NEXT STEPS (what we did wrong / where we need to improve)
Careful review of BOM
Careful review of production data
Mechanical integration
  Created problems during the last production batch with ITech
  No 3D model, no accurate 2D plans
  Do we try production without ?  man power issue
Schedule
  Sep. 15: Production of next version PZ16M prototype (PZ16M version2)
  Dec. 15: Deadline for validation of PZ16M-v2
  Jan.-Jun.16: Purchasing, production of PZ16M
  July 16: Installation/commissioning of PZ16M (too late!)
    Optimistic: small margin to get it done in time
    Pessimistic: we are already too late, we might have to install PZ16M after cool down
THANK YOU!