## Sheet1
Work Package: | WP19 | (please enter your work package number)
Document | Remarks (optional) | Approved | Conditions for approval/reasons for dismissal
XTL_R01
XTL_R01_DG3 |  | no because of | *WP19 has to deliver correct models of udulator vacuum chambers incl. Supports and intersections. No interferences expected. *No racks shown *Air conditioning system for undulators not shown.
XTL_R01_Interferences
XTL_R02
XTL_R02_DG3 |  | no because of | *WP19 has to deliver correct models of udulator vacuum chambers incl. Supports and intersections. No interferences expected. *No racks shown *Air conditioning system for undulators not shown.
XTL_R02_Interferences
XTL_R03
XTL_R03_DG3 |  | no because of | *WP19 has to deliver correct models of udulator vacuum chambers incl. Supports and intersections. No interferences expected. *No racks shown *Air conditioning system for undulators not shown.
XTL_R03_Interferences
XTL_R04
XTL_R04_DG3 |  | no because of | *Section up-stream QF.2946.T4D looks suspicious (see screenshot). *No cooling water for magnets required?
XTL_R04_Interferences
XTL_R05
XTL_R05_DG3 |  | yes
XTL_R05_Interferences
XTL_R06
XTL_R06_DG3 |  | no because of | *Concrete blocks have to be added. *No cooling water for magnets required?
XTL_R06_Interferences
XTL_R07
XTL_R07_DG3 |  | no because of | *BV.3070.T4D missing *No magnets supports shown. *BINP has to update model up to the point where the beam-pipe diameter increases. *No cooling water for magnets required?
XTL_R07_Interferences
Milestones
Rack Inventory

## Sheet2 (hidden)
yes
yes under the condition
no because of