## Sheet1
Work Package: | 17
Document | Remarks (optional) | Approved | Conditions for approval/reasons for dismissal
| General |  | The Racks are missing!
XTD4_R01_DG3 |  | no because of | - vacuum pipe missing (10 mm) - support structure for second BPM in the section (BPME.2800.T4) not complete, stone and everything missing. - support of BPME.2806.SA3 and quad missing. - support of BPME.2812.SA3 and quad missing. - Collision of pump port (strangely twisted) with BPM support in the intersections
XTD4_R02_DG3 |  | yes under the condition | - Collision of pump port (strangely twisted) with BPM support in the intersections will be removed
XTD4_R03_DG3 |  | yes under the condition | - Collision of pump port (strangely twisted) with BPM support in the intersections will be removed
XTD4_R04_DG3 |  | yes under the condition | - WP-17: 2 BPMA correctly integrated - Support of the vacuum pumps at 2961 an 2179 m look not complete and strange, two inconsitent models over each other? Pump still in DG2?
XTD4_R05_DG3 |  | yes under the condition | - No WP-17 components - supports for the ion getter pumps look incomplete
XTD4_R06_DG3 |  | no because of | - Support of ion getter pump at 3058 m, looks different as in room 4, more like DG2, pumps is not connected to the support. - Components at 3065 m: supports missing for Steerer, Quad, BPMF, Toroid - Dipol support at the end of the room is missing.
XTD4_R07_DG3 |  | no because of | - Magnet Supports are missing

## Sheet2 (hidden)
yes
yes under the condition
no because of