## Sheet1
Work Package: | WP32 | (please enter your work package number)
Document | Remarks (optional) | Approved | Conditions for approval/reasons for dismissal
XTL_R01
XTL_R01_DG3
XTL_R01_Interferences |  | yes | built as designed
XTL_R02
XTL_R02_DG3
XTL_R02_Interferences |  | yes | built as designed
XTL_R03
XTL_R03_DG3
XTL_R03_Interferences |  | yes | built as designed
XTL_R04
XTL_R04_DG3
XTL_R04_Interferences |  | yes | built as designed
XTL_R05
XTL_R05_DG3
XTL_R05_Interferences |  | yes | built as designed
XTL_R06 |  | no because of | PH-Pritschen, intersection with SLRS
XTL_R06_DG3 |  | yes | No intersection in detailed model
XTL_R06_Interferences |  | yes
XTL_R07 |  | no because of | PH-Pritschen, intersection with SLRS
XTL_R07_DG3 |  | yes | No intersection in detailed model
XTL_R07_Interferences |  | yes
Milestones
Rack Inventory

## Sheet2 (hidden)
yes
yes under the condition
no because of