## Sheet1
Work Package: | WP19 | (please enter your work package number)
Document | Remarks (optional) | Approved | Conditions for approval/reasons for dismissal
XS1 |  | no because of | see below
XS1_T1_DG3 | not in inbox | yes under the condition | * position of BSEC magnet incorrect * vacuum supports on "bridge" will be modified by MEA
XS1_T2_DG3 | not in inbox | yes under the condition | * position of BSEC magnet incorrect
XS1_TLD_DG3 | not in inbox | no because of | * OTRD.2121.TLD missing * TORC.2122.TLD missing * BHM.2122.TLD missing * supports BPMD.2101.TLD and BPMD.2118.TLD missing * dump-camera (WP17) not shown in model * mirror for dump-camera (WP17) missing * transversal movable girder not correct positioned * transversal position of main dump incorrect * muff of main dump not shown * SWEEP.2119.TLD is shown with different concrete supports * concrete blocks of BV.2111.TLD and QK.2113.TLD not in accordance with reality * concrete blocks for VCBSHUT.2130.T1 and VCBSHUT.2129.T2 missing * exhaust gas pipe of dump vacuum not correct, has to go above air channels (WP19) * air conditioning channel at XS1 entrance not in accordance with reality * before SWEEP.2119.TLD the water sealing is missing * emergency exit path in front of beam shutters wrong * several wrong and wrong positioned reference grounds in UG3 * at the position of the dump-pump a rack from WP20 is shown, which should not exist any more
XS1_Interferences | not in inbox | no because of | see remarks
Milestones | not in inbox | no because of | see remarks
Rack Inventory | not in inbox | no because of | see remarks

## Sheet2 (hidden)
yes
yes under the condition
no because of