## Sheet1
Work Package: | WP17 | (please enter your work package number)
Document | Remarks (optional) | Approved | Conditions for approval/reasons for dismissal
XS1
XS1_T1_DG3 |  | yes under the condition | Cable routing for BPMA.2131.T2 is needed, could go close to magnet cables. BPMA.2132.T2 situation looks strange, stone located wrong? BPMA.2145.T2 situation looks strange, stone located wrong?
XS1_T2_DG3 |  | yes under the condition | Collison of vacuum support with OTR support at 2147 m. Most probably already solved. Cable routing for BPMA.2139.T1 is needed, could go close to magent cables.
XS1_TLD_DG3 |  | yes under the condition | BPMD.2101.TLD fit with Ventilation according to the model, but is tight. Needs to be checked with reality. (Bad experience with an OTR system)
XS1_Interferences
Milestones
Rack Inventory

## Sheet2 (hidden)
yes
yes under the condition
no because of