## Slide 1: Injector Commissioning
Matthias Scholz
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)
Change the partner logos or add others in the last row.

## Slide 2: Injector and topics of this talk
Injector laser
Gun & gun section
A1
Diagnostic section
(Emittance measurements)
Laser heater
Long bunch trains/ losses
Magnets/ magnet model

## Slide 3: Commissioning schedule as presented in November 2015
Start | Jan 2016
Initial Commissioning Phase Goal: Reproducible and reliable beam transport for full bunch train length from the gun to the injector dump | 8 weeks
Intermediate Commissioning Phase (intermediate goal) Goal: Slice emittance is reproducible below 1mm mrad | 12 weeks
Final Commissioning Phase Goal: Nominal performance for all charge options and full bunch train length | 10 weeks
Optional Beam Physics Studies / Contingency Beam physics studies and improvement of performance beyond TDR goals… | 4 weeks
End | Sept 2016
April 2016
TDS for slice emittance measurements is not operable yet but projected emittances are < 1.5 mm mrad.
Nominal performance has been achieved for many beamline elements.

## Slide 4: Injector commissioning minimum goal as presented in November 2015
Achieve parameters to enable first lasing
Quantity | Value
macro pulse repetition rate | 10 Hz
RF pulse length (flat top) | 100 ms
bunch repetition frequency within pulse | 1.0 MHz
bunch charge | 0.5 nC
Slice emittance (about 50 MV/m gun gradient) | 1.0 mm mrad
Achieved
10 Hz
650 ms
4.5 MHz
100 pC – 1 nC
Not possible yet
Projected emittance (52 MV/m gun gradient) | 
1.2 mm mrad

## Slide 5: Injector commissioning goal as presented in November 2015
Achieve all XFEL TDR parameters
Intermediate Goal: Achieve all XFEL TDR parameters but not for full train, i.e. no operation of gun with high gradient and long RF flat top simultaneously.
Quantity | Value
macro pulse repetition rate | 10 Hz
RF pulse length (flat top) | 600 ms
bunch repetition frequency within pulse | 4.5 MHz
bunch charge | 0.02 – 1 nC
Slice emittance (req. 60 MV/m gun gradient) | 0.4 - 1.0 mm mrad
Achieved
10 Hz
650 ms
4.5 MHz
100 pC – 1 nC
Not possible yet
Current setup is:
  Gun gradient ~53 MV/m < 60 MV/m
  Pulse length 650 ms

## Slide 6: First beam in the gun section and injector cooldown
November 25. Betriebserlaubnis (operating license)
December 9, start cool down of the the injector. 1st time at this temperatures for AH1.
December 14, injector is cold (warm compressors).
December 15, stable 2 k in the injector (cold compressors).
December 8, first beam in the gun section (TORA.25.I1). Self triggered mode -> shown at 700 us.

## Slide 7: Accelerating module A1
Cavities were tuned to 1.3 GHz between December 16. - 18.
December 18. rough calibration of all cavity signals
December 18. All feedback loops were closed and module was running with nominal amplitude.
Cavity phasing of A1 was achieved January 9. 2016.

## Slide 8: Electron beam in the injector dump
December 18, A1 is operational, electron beam with 130 MeV in the dump.
December 21, first emittance measurements.

## Slide 9: Injector laser with diffraction pattern
  The appearance of the QE maps could not be explained with a nice laser spot on the cathode.
  The required laser power for certain bunch charges was higher than expected.
  Moving the laser on the near field camera moved also the electron beam on the first BPMs (not expected).
There were indications that the injector laser did not hit the cathode directly but is reflected at the vacuum chamber.
  Strange electron beam shapes on the first screen in the gun section. The wings and tails could be changed with different solenoid currents but did not disappear.
QE map

## Slide 10: Injector laser after correction
Realigning the laser from UG5 to UG7 did not change the diffraction pattern.
The reflection took place between the last mirror which is positioned inside the vacuum chamber and the cathode.
The cathode was removed and the mirrors were readjusted using a green alignment laser.
After that, the electron beam spot and the QE maps looked like expected.
Laser alignment
QE map
Electron beam on OTRC.56.I1

## Slide 11: Reliability of the electron gun
Power [MW] | Pulse length [µs] | duration [h] | integrated energy [GJ] | Date run end | time | Reason for end
4.5 | 654 | 8 | 0.847584 | 21.3. | 5:35 | photo diode air side / reflected power
4.5 | 670 | 5 | 0.5427 | 23.3. | 21:53 | Klystron 1 refl. Power
4.5 | 670 | 12 | 1.30248 | 24.3. | 11:20 | Gun refl. Power
4.5 | 670 | 3 | 0.32562 | 24.3. | 18:46 | Gun refl. Power
4.5 | 670 | 42 | 4.55868 | 28.3. | 14:23 | Gun refl. Power
4.5 | 670 | 7 | 0.75978 | 29.3. | 00:12 | klystron and Gun refl. Power
4.95 | 665 | 3 | 0.355509 | 1.4. | 17:43 | Spark Win, air side
4.95 | 650 | 45 | 5.21235 | 10.4. | 10:41 | Gun refl. Power peak
4.95 | 650 | 3 | 0.34749 | 10.4. | 14:20 | Gun refl. Power peak
4.95 | 650 | 33 | 3.82239 | 12.4. | 02:14 | Gun refl. Power peak
4.95 | 620 | 6 | 0.662904 | 13.4. | 17:51 | Gun refl. Power peak
4.95 | 620 | 39.5 | 4.364118 | 19.4. | 04:45 | Spark Win, air side
 | RepRate | 10 |  | Hz | 
h | days | # IL from gun only |  | days/IL | 
607.3 | 25.30 | 12 |  | 2.11 | 

## Slide 12: Restarting the electron gun by hand
Restarting the gun by hand takes typically 1 hour.
Typically the gun gradient is increased with a small RF pulse length (~20 us).
Then the pulse length is increased to the required length (650 us).
It is important to watch the gun temperature in order to stay on resonance. This keeps the reflected power low.

## Slide 13: Fast restart of the electron gun using the FSM
There is the possibility to restart the gun much faster
  LLRF parameters can be adjusted such that the resonance conditions are always fulfilled while ramping up the gradient and the pulse length.
  The water temperature regulation is disabled during the fast restart in order to avoid an overshooting gun temperature at the end of the ramp.
  Tests showed that the gun can ramped up within minutes to gradients of 55 MV/m and pulse length of e.g. 160 us. Experts are optimistic that this method can also be used for the maximum pulse length. Further test will be carried out soon.
April 14, 2016

## Slide 14: Reliability of capacitors in the matching networks and modulators
January 12, 2016
  A capacitor in the matching network of the gun failed. It turned out that they can not handle the 10 Hz pulsed operation.
  The matching network was replaced by MKK within 24h.
  Machine operation was restarted with 2 Hz. Back to 10 Hz operation January 28.
  The matching networks will be replaced every three month until a solution for the capacitors is found.

## Slide 15: Electron beam in the gun spectrometer
It was difficult to find the electron beam spot on the screen in the gun spectrometer.
It was verified that the screen is coated. The camera was exchanged.
With 30 bunches per train and an integration over several bunch trains it is possible to evaluate the pictures.
Further investigations are necessary to understand why this screen shows different results compared to the screen in the straight beamline.

## Slide 16: Electro Optical Detector
First electron bunch length measurements could be achieved using the EOD.
Picture shows preliminary results and more data evaluation is required.

## Slide 17: Magnet model and trajectory responses
Trajectory response measurements show a nice match with the theoretical predictions.
  The tool is working fine.
  The optics model used in the optics server is correct.
  The measurements proof that the magnet model is very nice.

## Slide 18: Injector operation with 2700 bunches
March 19, 2016: 2700 bunches with ~250 pC in the injector for the first time.
Number of bunches
Losses
Transmission
Integrated charge

## Slide 19: Impact of the injector laser on the cathode
The QE maps taken February 22 and March 22 show the impact of the injector laser on the cathode.

## Slide 20: Injector Diagnostic Section
Emittance measurement tool for 4 screen method
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 21: Emittance measurement setup
https://xfel-wiki.desy.de/Emittance_Measurement
Equal conditions for all emittance measurements
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 22: Emittance measurement parameters
Parameters changed for different measurements:
  Bunch charge (main focus on 500 pC case)
  Solenoid current
  Solenoid alignment
  Laser spot position on cathode
  Gun phase
  Beam optics (matching)
  Diameter of BSA
  …
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
If you want to use more partner logos position them left beside the DESY logo in the footer area.
Close Master View

## Slide 23: Emittance measurements using four screens in the diagnostic section
Projected emittances around 1.0-1.4 mm mrad could be achieved for a 500 pC beam.
  Using the third harmonic module AH1 increases the projected emittances by about 15%. This needs further investigation.
  All tools/routines for the slice emittance measurements are available and can used when the TDS is in operation
  Typical measurement for a 500 pC beam:
Plane | Emittance | BMAG
horizontal | 1.26 mm mrad | 1.24
vertical | 1.08 mm mrad | 1.16
Plane | Emittance | BMAG
horizontal | 1.37 mm mrad | 1.02
vertical | 1.04 mm mrad | 1.07

## Slide 24: Emittance measurements with off-axis screens
Emittance measurements with off-axis screens are much faster and can be done during user operation.
Different bunches in the bunch train can be studied.

## Slide 25: Longitudinal laser profile and laser stacker
Investigate influence and operation of flat top laser pulses
Gain material | Yb:YAG
Intra burst repetition rate | 4.5 MHz, 3 MHz, 1MHz, 100 kHz
Pulse width (FWHM) | Phase 1 (MBI): Short pulse: < 3 ps Long pulse: ~10 ps Phase 2 (DESY): Shaped 20 ps with 2 ps rising edges
Energy per pulse in burst | > 0.7 µJ pP @ 3 ps > 3 µJ pP @ 10 ps
The reduced space charge effects should lead to a smaller projected emittance.
This effect could not be seen yet. We need more time for further studies.
Laser pulse stacker is in operation since April15.
Pulse length is 26.2 ps (FWHM) at the moment.
W. Decking, MAC Nov. 2015

## Slide 26: Laser heater
The laser heater undulator can be controlled remotely.
The infrared laser was successfully aligned to the second laser table in the injector.
Test with the laser stabilization system showed very good results.
The vacuum in the laser beamline is still fine when the mirror motors are moving.
Vacuum in the laser beamline
First laser table in the injector
Position feedback
IR Pulse

## Slide 27
Thank you for your attention!