## Slide 1: Zugang zu den Undulatoreinhausungen am Beispiel von SASE1
J. Pflüger, WP71

## Slide 2: Status SASE1
Undulator hardware installed
Vacuum system installed -- operationaö
Control system installed and wired – operational
Control System operational, can be remotely controled
Installation of enclosure started not yet finished
Status: 18.5.2016

## Slide 3: SASE1 Next Steps
Complete enclosures - until 31.5.2016
Do remaining work inside the enclosures:
  BLMs: in work
  Pilotherme cables: in work
  220V Connectors: promised
  Quadrupole Covers (Sicherheitsabdeckungen): in work
  Magnetic clamp of laser fiducial (Haftmagnet in Vermessungsmarke): known
  Tunnel search (Flash lights, loudspeakers, …..??? ) status unclear
  More ?
Hardware commissioning, hot commissioning phase:
  Remove wooden safety covers and protective foils
  Adjust vacuum chamber and undulator close gap to 10.000mm
  Adjust Hardstops, limit switches and CALs
  Mount and adjust RADFETs
  Mount and align Air Coils and connect cooling water
 Ready for Operation

## Slide 4
Removal of protective covers:
Safety issue  Precautionary measures needed  discussed with SAVE

## Slide 5: New Hazards
Only inside the enclosure after removal of protective covers
Strong magnetic fields
  Danger with magnetic tools
  Danger for bearer of implants (Implantatsträger) Cardiadic pacemaker etc.
  Danger for credit cards, bank cards etc.
Crushing Hazard (Quetschgefahr) by slowly moving parts
  Max. gap speed 10mm/s
  Remote control of undulator maybe enabled

## Slide 6: Consequences
Removal of protective covers defines beginning of new safety regulations inside the enclosures:
Inside the enclosure it is very tight and space is very limited
Keep enclosure closed and stay out. It is the best, 100% protection
Strict access control for un-avoidable work:
  Control / approval / permission through WP71
  Instructions/tutorial by WP71
  No magnetic tools!

## Slide 7: Measures
Keep enclosures closed
  There is a door in every cell with a handle and a lock.
Restrict access by announcement
Attach warning and instruction signs in agreement with SAVE on every nth cell n= 1..5

## Slide 8
In der Einhausung Gefährdung durch:
Starke Magnetfelder durch offene, starke Permanentmagnete, die nicht abgeschaltet werden können.
Quetschgefahr durch bewegliche, ferngesteuerte Magnetstrukturen
Vorsichtsmaßnahmen:
Türen und Seitenwände immer geschlossen halten
Kein Zutritt für Träger von Herzschrittmachern und Implantaten
Kein magnetisches Werkzeug: Verletzungsgefahr
Gefahr der Beschädigung von Uhren, Bank-, Scheck- und Kreditkarten
Zutritt und Arbeiten nur nach Absprache und Einweisung durch die XFEL Undulatorgruppe, WP71.
Kontakt: G.Deron, 3341; S. Karabekyan, 4797 J. Pflüger, 3242 M. Yakopov, 5635
Undulatorsystem im Testbetrieb!

## Slide 9: Appeal (Appell)
To all having work in the XTD2 enclosures:
Do all work as soon as possible, especially
  BLMs:
  Pilotherme cables:
  220V Connectors:
  Quadrupole Safety Covers (Sicherheitsabdeckungen):
  Magnetic clamp of laser fiducial (Haftmagnet in Vermessungsmarke):
  Tunnel search (Flash lights, loudspeakers, …..??? )
Work in XTD4 and XTD1 Convenient access if neither phase shifters, undulators and enclosures are installed.
Installation Plans for XTD4:
  Phase Shifters by 27.5. ; Undulators by 10.6.
  Enclosures in July
Installation plan for XTD1
  Same procedures in 4-5 months