## Sheet1
Schedule and Milestones
Release 2.1 completed | 2006-10-31 13:30
Release 2.2 completed | 2006-12-30 13:30
Linux version ready | 2007-02-15 14:00
Semimobile Hardware set up beta version | 2007-02-15 14:00
Help System beta completed | 2007-02-15 14:00
Full scope of VI available | 2007-05-01 14:00
tests starts | 2007-01-02 13:30
ends | 2007-03-31 13:30
face to face meeting to fine tune design | 2007-02-22 14:00
Specification update | 2006-11-14 13:30
Design Report | 2007-06-29 13:30
Implement final version of GANMVL | 2007-06-29 13:30
Extended Collaqboration Workshop | 2007-09-15 08:00
evaluation expert review | 2007-01-15 14:00
simulation test +eval | 2007-02-14 14:00
eval of field tests | 2007-10-01 14:00
final evaluation report | 2007-12-31 14:00