## Slide 1: WP74 installations in XTD1 (SASE2)
J.Grünert, F.Dietrich, A.Koch, W.Freund
X-ray Photon Diagnostics Group (WP74)
European XFEL
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)

## Slide 2: Overview of WP74 installations in XTD1
K-monochromator System
  Filter Chamber
  K-Mono
Imagers
  Transmissive Imager
  SR Imager
  FEL Imager
X-ray Gas Monitor (XGM)
Gas supply system

## Slide 3: K-Mono system for XTD1, SASE2
LA = 2577 m, Filter Chamber
  Appr. 0.4 x 0.5 x 1.5 m3 (LxWxH), 60 kg
  Transport on transport frame with wheels
  Ready for installation now (at XHE3).
LA = 2586 m, K-Mono
  Appr. 1.6 x 0.7 x 2.5 m3 (LxWxH), 850 kg
  Transport on wheels or with forklift truck (?) (maybe without SR-Imager mounted, as we have to pass the XGM frame in XTD1)
  position in tunnel: on ramp!
  RFI planned April 2017

## Slide 4: Imager in XTD1, room 10-11, SASE2
Imager for XTD1, room 10-11, SASE2
LA = 2577 m, Transmissive Imager
  Appr. 0.3 x 0.4 x 0.9 m3 (lxwxh), 50 kg
  Transport on Euro-palette
  Ready for installation.
LA = 2585 m, SR Imager
  Appr. 0.6 x 0.7 x 0.5 m3 (lxwxh), 60 kg
  Transport on Euro-palette, RFI Dec. 2016
LA = 2637 m, FEL Imager
  Appr. 1.0 x 0.8 x 0. 6 m3 (lxwxh), 40 kg
  Transport on Euro-palette, RFI Jan. 2017
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
Close Master View

## Slide 5: XGM
Device Installation
  Q2 - 2017
Size & Weight
  Girder with chambers: ca. 700 kg;
  0,85 m x 3,0 m; beam ca. 2,30 m
  Pillars and support:
  >600 kg

## Slide 6: Tunnel situation at XGM location

## Slide 7: Gas Supply
Scheduled installation date in XTD1: mid-October 2016 (ca. KW42)
Panel: ca. 500mm x 1700 mm (Width x Height), 230 mm panel depth
Connection of the gas pipes delayed by missing cross-support (MKK Säulenausleger)
Dräger will inform with „Behinderungsanzeige“ if connection is not possible in KW45

## Slide 8: XGM support XTD1
Installation situation w42
View towards the beam
Gas Panel placed

## Slide 9: XGM support XTD1
Installation situation w44
View towards the beam
Passing height (at lowest
point of blue structure):
225cm (measured)
Transport Path height:
210cm

## Slide 10: Top view of floor, actual dimensions (in cm, measured)

## Slide 11: Thank you for your attention