## Slide 1: First 4 weeks of commissioning
Winni Decking
DESY
COMeeting, 14.12.16

## Slide 2: Status 2.1.2017
Injector @ 2K with AMTF warm pumps
L1-L3 @ 4K, start cold-compressors to pump down to 2K
MKK technical commissioning of XTL warm magnets finished
XTL personnel interlock approved
CS1-CS7 RF operable

## Slide 3: Week 1&2: 2.1.-16.1.
Injector - re-commissioning
  Tune 1.3 & 3.9 GHz cavities
  Re-commission LLRF system
  Establish operation with 0.5 nC, 60 bunches, < 1 mm mrad slice emittance
XTL - accessible for planned work
  1900++: finalize cabling (vacuum and diagnostics)
  L1-L3: start cold-compressors to pump down to 2K, establish stable operation
  BC2: tune TDS structure, connect wave-guides
  All warm beamlines: polarity and control system checks of all magnets

## Slide 4: Week 3: 16.1-23.1
Injector – provide beam
  Beam commissioning of dogleg in XSE shaft
XTL – tunnel closed, personnel interlock set
  L1-L3: Start tuning cavities on resonance
  L1-L3: Start commissioning of cold magnets
  L1: LLRF no-beam commissioning (1 RF station, 4 modules, low power)
  L1, B1: Pass beam into BC1 dump at 130 MeV

## Slide 5: Week 4: 24.1 – 30.1
Injector: Provide beam
L1: LLRF commissioning with beam up to 600 MeV
B1: Commission BC1 with 600 MeV
  L2: start LLRF no-beam commissioning (3 RF station, 12 modules, low power)
  L3: Tuning cavities on resonance
  L3: Commissioning of cold magnets