## Slide 1: Status of XFEL mirrors
Harald Sinn
X-ray Optics
6.1.2017

## Slide 2: Horizontal deflecting mirrors for beam transport
3 x Type A (SESO pre-polish, JTEC final polish) for benders
6 x Type B (JTEC) for non-bendable mirrors
1 x Type A (SESO pre-polish, JTEC final polish): spare
2 x Type A (SESO pre-polish, ZEISS final polish)
All JTEC mirrors were received in 2016 and polishing and shape is within specifications
ZEISS mirrors received, but did not fully reach specs (5-8 nm PV)
2 JTEC-mirrors coated with B4C at HZG and returned to XFEL
5 more JTEC-mirrors at HZG and in process of coating

## Slide 3: Vertical deflecting mirrors/gratings for SASE3 beam transport
2 Pre-mirrors (JTEC) for soft mono: Low-energy mirror received and OK. High energy mirror was damaged at JTEC and will be replaced in January (damaged mirror has also finish in specs). Shape of both mirrors according to outdated drawings, one cooling structure of mono has to be changed.
2 short commissioning gratings (150 mm) with 50l/mm received from Horiba Jobin-Yvonne. Specs barely OK, still in XFEL metrology. Will be B4C coated after HZB metrology.
Long gratings: 6 substrates exist, 2 superpolished by Zeiss, barely in specs but finally accepted. One will be B4C-coated without ruling.
After large HZB ruling machine not becoming operational, new hope exists now (Jan17) that HJY can rule also 500 mm long gratings (50l/mm and 25 l/mm) with substantial extra effort.

## Slide 4: Instruments mirrors: MID
2 cryo-cooled mirrors produced by ZEISS barely in specs. Several rounds of metrology measurements at ZEISS, HZB and XFEL to verify specifications (XFEL measurements finished in December).
Will be coated in March 2017 (please confirm coating specs).

## Slide 5: Instrument mirrors: SPB
4 mirrors for µ-KB (JTEC, contractor FMB-Oxford): Were ready by end of December, however waiting for 2/4 metrology reports from JTEC before shipping. MHE OK, MVP needs to be re-worked by 50 nm, because wrong FEA was used. Probably all 4 mirrors will be shipped in January/February (still in JTEC schedule).
2 mirrors for nano-KB (JTEC, contractor FMB-Oxford): Expected to be polished by end of March 2017

## Slide 6: Instrument mirrors: SCS
2 bendable side-shaped KB mirrors + 1 vertical deflecting mirror (JTEC, contractor FMB-Oxford):
Were finished ahead of schedule (Dec. 2016 vs March 2017), however, the shape of substrate was finished according to wrong drawings. Substrates are not able to work with bender, holding & cooling schemes. Focus close to nearest focus spot. Metrology reports not yet received. The current view is to not accept or ship these mirrors (under discussion). Replacement mirrors should be ready in September 2017.

## Slide 7: Instrument mirrors: SQS
2 bendable KB-mirrors (1 m long and side-shaped, JTEC, contractor FMB-Oxford):
Delivery date was end of April 2017. However, it turned out, that these substrates were also manufactured according to wrong drawings. Fine-polishing has not yet started. Shape and focus point of pre-polished substrates completely wrong.
New estimated delivery date is now December 2017.