## Slide 1: Petal cores and module-on-core mounting
Sergio Díez (DESY), Bernd Stelzer (TRIUMF)
Core concept, manufacture steps, infrastructure
Production flow for cores at DESY
Specs and QC
Module-on-core concept
Module-on-core specs and QC
Endcap production preparation meeting
March 3rd, 2017
DESY Zeuthen

## Slide 2: Petal core concept
Staves and petals require low-mass cores with embedded cooling pipes, good thermal performances, resistance to deformations, flat structure
Carbon composites: tremendously flexible class of materials, reasonable Xo, good thermal properties, variable CTE
  Carbon fiber “sheets” consist of filaments or woven layers impregnated with epoxy.
  By arranging layers in various lay-ups and configurations, a great variety of components can be created with enhanced mechanical and thermal properties

## Slide 3: Latest petal core design (Feb 2017)
5.0 mm core thickness (from surface of bus tape to surface of bus tape)
Cut-out at the EoP region to allow rapid bending of the pipe
Electrical break outside the core structure
Pipe inlet and outlet next to each other, no PL in between
Through-holes at PLs
5 mm oversized hole at unconstrained PL
Latest CAD model here

## Slide 4: Core manufacture tools
Core manufacture performed with precision tools tools in order to obtain
  Required accuracy
  Repeatability
  High throughput
Toolset in constant evolution, along with core layout
  Converging on a final design
    Expect only minor changes in the design from now on (although I have been making this statement for more than 2 years...)

## Slide 5: Current manufacture steps + infrastructure
Step # | Description | Infrastructure
1 | Cutting and co-curing of 0-90-0 facesheets + bus tapes | Pattern cutter, Autoclave
2 | Cutting of full set of glue masks for core manufacture | Pattern cutter
3 | Pipe bending and brazing of StSt pipe fittings | Large vacuum brazing oven, pipe bender
4 | Machining of top and bottom closeouts with petal locators | CNC milling machine
5 | Gluing of top and bottom closeouts on bottom facesheet | Core tools
6 | Machining of graphite (Allcomp) foam | CNC milling machine
7 | Gluing of cooling loop (foam to pipe) | Core tools
8 | Gluing of cooling loop (loop to bottom facesheet) | Core tools
9 | Machining of carbon fiber C-channels | CNC compatible with CF materials
10 | Gluing of carbon fiber C-channels | Core tools
11 | Cutting of carbon fiber honeycomb to shape | Pattern cutter
12 | Gluing of carbon fiber honeycomb | Core tools
13 | Milling of core surface | Milling machine compatible with CF
14 | Gluing of top facesheet | Core tools
15 | Precise machining of petal locators | Large range CNC (> 600 x 350 mm)

## Slide 6: Rough FTE time estimates per core
1-2 hours work ½ day work Full day work > 1 day work
Step # | Description | Infrastructure
1 | Cutting and co-curing of 0-90-0 facesheets + bus tapes | Pattern cutter, Autoclave
2 | Cutting of full set of glue masks for core manufacture | Pattern cutter
3 | Pipe bending and brazing of StSt pipe fittings | Large vacuum brazing oven, pipe bender
4 | Machining of top and bottom closeouts with petal locators | CNC milling machine
5 | Gluing of top and bottom closeouts on bottom facesheet | Core tools
6 | Machining of graphite (Allcomp) foam | CNC milling machine
7 | Gluing of cooling loop (foam to pipe) | Core tools
8 | Gluing of cooling loop (loop to bottom facesheet) | Core tools
9 | Machining of carbon fiber C-channels | CNC compatible with CF materials
10 | Gluing of carbon fiber C-channels | Core tools
11 | Cutting of carbon fiber honeycomb to shape | Pattern cutter
12 | Gluing of carbon fiber honeycomb | Core tools
13 | Milling of core surface | Milling machine compatible with CF
14 | Gluing of top facesheet | Core tools
15 | Precise machining of petal locators | Large range CNC (> 600 x 350 mm)

## Slide 7: Some pics
Co-curing of facesheets + bus tapes
Gluing of pipe to foam
Cooling loop
Honeycomb cut to shape
Milling of petal surface
Petal ready for second facesheet
Bus tape before and after co-curing

## Slide 8: Remarks
At the moment, DESY Hamburg is performing every single step on this list (with the exception of the currently co-cured bus tapes, performed at Liverpool, but planned at DESY once our autoclave is operational)
Parallelization of work is definitely needed (see next slides)
Machined parts could be (should be) manufactured in industry
It will help if some institutes help in producing some of these parts
  Or even better: produce cores!

## Slide 9: Core production flow at DESY
Carbon-fiber pre-pregs
Carbon-fiber honeycomb
Pultruded carbon fiber rods
Carbon fiber foam
Titanium pipes
Petal bus tapes
43a
Carbon fiber lab
DESY Workshops
Petal core assembly
Facesheets + bus tape co-curing
Cooling loop assembly
Petal assembly
Transport to Geb. 26
Final precision PL machining
Reception tests
Thermoplastic materials
Industry
Industry
JSI Ljubljana
Industry
Industry
Industry
Industry
Petal locators and closeouts machining
Pipe bending
Pressure and He leak tests
Machining of foam
Machining of C-channels
Pipe connectors and E breaks vacuum brazing
Connectivity test

## Slide 10: DESY HH ITk Schedule
 | 2017 |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  | 
Cores (422) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Modules (XXX) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EoS boards (XXX) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Petals (100) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EC integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EC commissioning (DESY) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EC transport, installation, and commissioning (CERN) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-production readiness
Pre-production
Production
Throughput:
~4 cores per week over 2 years
Contingency: extend production time by ~6 months?

## Slide 11: Specs and QC
Quality control steps
  Ti pipes: Pressure and He leak testing after bending and brazing
  Machined parts (C-channels, closeouts, Allcomp): Optical tests with SmartScope
  Bus tapes: Impedance and BERT tests before co-curing, after co-curing, after core build
  Completed cores:
    Geometrical
      Overall Flatness
      Local flatness
      Delamination tests
      Parallelism?
      Torsional strength?
    Thermal/combined
      IR tests (-30 C, CO2 dual-phase)
      Thermal cycling
  Some of the test stands under development at the moment, SmartScope CNC 670 a key equipment for this
Expect core (and module-on-core) specs by March AUW

## Slide 12: Industrial approach: Scientifica
IFIC-Valencia is trying to qualify this company for petal core production
  Progress on this has been heavily delayed due to lack of titanium pipes (don’t get me started)
  However, they already have all the materials for building their first petal, including co-cured v1 bus tapes (many thanks Luise P., Peter C., Tim J.)
  They want to try an alternative way of connecting to the pipe with injected, T conductive foam
  They will need co-cured bus tapes anyway (DESY HH), probably also brazed Ti pipes
  Expect some results in the near future
  At this stage, the idea is that they produce a prototype petal that we should “qualify” in order to decide if we leave petal core production to industry (DESY should help with this)
Scientifica.es

## Slide 13: Available cores and summary
R&D on petal core manufacture is being carried out by DESY HH
  4 cores produced so far
    1 thermo-mechanical petal
    1 full core at DESY for mechanical studies
    2 dummy cores (no pipes) devoted to module-on-core studies
  2 more cores underway
    With pipes, without bus tapes
    1 standard core, 1 “thin” core (5.0 mm thick)
Machining of all the core components is dragging us down really badly
  Investigation of outsourcing machining to industry ongoing
    Quite likely for COs and C-channels
    Very unlikely for Allcomp foam and core milling
DESY will most likely not be able to produce all the cores for both endcaps, especially considering the commitment on other areas too
  Industrial approach with Scientifica followed up by Valencia, DESY is getting involved on this
  Any other volunteers within the community welcome

## Slide 14: EC module-on-core (I)
Active EC Sites:
DESY, Freiburg, Valencia, Vancouver
Requirements: Accurate placement of modules on petal core and good cooling connection, tools include:
Robotic x-y-z gantry (optical survey, glue deposition?)
Generic module loading station
Module loading bridges (x-y translation, rotation)
Petal metrology (vision CMM or laser range finder)
Assembly frames:
  Outer frame mounted to gantry table, supports bridge
  Inner frame holds petal (also during bonding and shipping?)
Common Procedure:
Survey petal locators to determine petal reference frame
Load EC module from loading station onto bridge
Survey module fiducials and (iteratively) position module
Apply glue pattern of SE4445
Place module – cure glue, held in place by bridge – repeat 9 times
Perform post-mounting petal metrology survey
Wire bonding to bus-tape and EoS + electrical acceptance test
Common tooling on sharepoint

## Slide 15: EC module-on-core (II)
Specifications (similar to barrel)
Components
  Local flatness of core ±25µm
  Module bow between -50µm and +150µm (negative means center above edges)
  (Bus-tape) pads within 100µm in y and 300µm in x
Equipment:
  Repeatability of gantry position <20µm in all directions
  Out of plane metrology accuracy <10µm
Performance Target:
  Placement of modules with a lateral accuracy of ±50µm (i.e. no point between 2 modules closer than 400 µm)
  Average distance between sensor and core is 150µm (to ensure good cooling contact)
Details of Checks/QC/QA:
Components in the loading process shall be checked on reception
Perform a electrical acceptance test using GBT link (QC)
Thermal cycling of loaded petal (QA only)?
https://cds.cern.ch/record/1514636
Module loading specifications being defined. Draft: (Google doc)

## Slide 16
Backup

## Slide 17: Petal Coordinate System
The back side is a 180 degree rotation of this around the X axis
Note: R0 has been designed with -4 mrad (The decision to go for 3.5 mrad came a bit later)

## Slide 18: Sensor Coordinate System
Beam reference frame with a sensor placed at the desired radius R from the beam-line and rotated by the stereo angle. The Sensor-frame is centred at O; the Strip-frame is centred at f .

## Slide 19: Modules on Petal
Sensors are placed by positioning the centre of the wafer (Ow) at a given radius ( and angle)
Blue markers tell about the radius (E)
Brown markers give the corners of the sensor (F)
Red markers help defining Ow (G)
Green markers are for the angles (markE)

## Slide 20: Modules on Petal
Crossing point at (0,0), ie, interaction point.
The angle (which accommodates the 3.5 mrad and the rotation in the outer rings) can be defined by 3 lines (blue) that cross at the origin (interaction point).