## Slide 1: Accomplished tasks this week (XTD2)
Differential pumping
  No change since last week
  Waiting for CAS
PBLM
  Motors and Encoders wired
Mirror chamber 2
  Closed again and under vacuum
  NEG pump installed
Fast valve
  Local test with AE done
    But not yet included in PLC-loop
Thermocouples wired to equipment protection crate
  Collimator
  Absorber
  Frontend in XS3
Interface to WP-19
  MVS will continue in week 7 with compressed air installation and missing limit switches

## Slide 2: Accomplished tasks this week (XTD9)
Whole SASE1 Photon Vacuum System
  System pumped, leak tested
  All ion pumps switched on
SPB devices
  Solid Attenuator Pule Picker under vacuum
  Cables for CRL were pulled
FXE Si-Monos
  Internal wiring finished
  Under vacuum
Fast valves
  Local test with AE done
    But not yet included in PLC-loop
PBLM (FXE & SPB)
  Motor and Encoder cabling almost done
  Ready for local test mid of next week
DP – XGM – DP
  Local test started yesterday
  Small cabling issues found
    Will be solved in the next days