## Slide 1: Accomplished tasks this week (XTD2)
Differential pumping
  No change since last week
  Waiting for CAS
  Preparation for XGM repair
PBLM
  Motors and Encoders wired
Mirror chambers
  Local test of motors and encoders done
  Problem with one encoder, fixed yesterday, needs testing again
Fast valve
  Local test with AE done
SRA (PSLIT)
  Local test finished yesterday
  Cooling water connection next week
Interface to WP-19
  MVS will continue next week with compressed air installation and missing limit switches
  Our cables are ready

## Slide 2: Accomplished tasks this week (XTD9)
Fast valves
  Cable for MPS connection pulled
PBLMs
  Motor and encoder cabling done
  XTD9 med. priority PBLM wired
  Ready for local test mid of next week
DP – XGM – DP
  Almost ready
  More cabling issues then expected
  Test setup in vacuum lab prepared for AE to test serial communication