## Slide 1: Progress on Imagers in SASE1
Andreas Koch
WP74
16.2.2017

## Slide 2: Status installation of Imagers SASE1
This week:
  Rework on connectors and cabling done for all imagers.
  Waiting for Karabo access in tunnel.
  Start with cabling of timing signal.
  RFI for XTD10 imagers 1x Pop-In I und 1x Pop-In II-45.
Next week:
  Start Karabo tests.