## Slide 1: Update critical task list
3.3.2017

## Slide 2: What has been achieved in 2017:
Labs E0 XHQ
Sanitary installations XHEXP1 / SASE1
Smoke extraction simulation & test successful
Openings in balcony rooms + pumps rooms closed
Cabling + Beckhoff crates + XML exports FXE / SBP-Optics mostly done
Phase II cabling for SPB in XTD9
Control room PCs + monitors
DAQ network + server infrastructure

## Slide 3: Hot topics
Fire safety: XHEXP1 issues: 31.3.2017
Beckhoff loops FXE and SPB-optics: first two loops each to be taken into operation ASAP
Fire safety: Closing of SASE1 rackrooms: Beginning of April (FXE) End of May (SPB)
Beamshutters SPB/SFX + FXE in XTD9: 31.3.2017
Beamshutter D.02: 30.4.2017
Interlock tests / TÜV tests XHEXP1: 19.5. / 29.5.2017

## Slide 4: Regarding detectors
Current scenario to be followed by WP75 after discussion with MB:
LPD ready for E2E-test: 1.3.2017
LPD E2E-tests done: 19.5.2017
LPD installed at FXE: 4.8.2017
Preparatory works for AGIPD E2E-tests: 22.5.2017
AGIPD E2E-tests done: 14.7.2017
AGIPD installed at SPB/SFX: 20.10.2017