## Slide 1: XGM – progress week 9 / 2017
Dr. Jan Grünert
X-ray Photon Diagnostics
Group Leader
Hamburg, March 3rd, 2017
Contains information from WP74 team
and from K.Tiedtke / F.Jastrow from DESY-FS-FL-D

## Slide 2: XGM - Progress (w9)
XGM@XTD2
  Water cooling for turbo pumps installed and operating
XGM@XTD9
  HV test and pulse tests on XGM@XTD9: DONE / OK
XGM@XTD10
  Particle Test performed: OK (initially a few counts, after 5min N2-flushing no counts)
  Repair (exchange by DESY of resistors in both XGMD-chambers): DONE
  Pump-down after repair  9E-6mbar (Thursday 15h30h)
  Leak check: OK
Grounding : check actual ground connections XTD2+9+10 with experts (Friday 24.2.)
Assembly of second crate ADAM&FEMTO (for XTD9): DONE
Gas Supply System: VOB Abnahme DONE

## Slide 3: XGM – Repair Progress Summary (w9)
XGM | Preparation | Resistor exchange | Leak test | HV test | Survey
HERA XGM01 | done | done | done |  | 
XTD2 XGM02 | done | done | done | done | done
XTD9 XGM04 | done | done | done |  | 06.03.
XTD10 XGM07 | done | done | done |  | (06.03.)
XHE3 XGM05 |  |  |  |  | 
XHE3 XGM06 |  |  |  |  | 

## Slide 4: XGM - Plan week 10
Planning of Next Repairs
XGM@XTD9: wiring of vacuum-to-Beckhoff This was started but delayed because Torben Falk is sick since last week Thursday.
Installation of ADAM&FEMTO crate in XTD9, Installation of cables at XGM@XTD9
Installation of XGM Electronics Crates (MTCA, HV) in XTD10