## Slide 1: Status of Beckhoff components
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)

## Slide 2: Production SASE3
Production SASE 3 (acc. to Redmine) |  |  |  |  |  |  |  |  |  |  |  |  | 
 | OCT | NOV | DEC | JAN | FEB | MARCH | APR | MAY | JUNE | JULY | TOTAL |  | 
DONE | 0 | 1 | 0 | 13 | 12 |  |  |  |  |  | 26 |  | 
INITIAL FORECAST | 0 | 0 | 4 | 17 | 22 | 22 | 20 | 0 | 0 | 85 | 85 |  | 
FORECAST 01.02.2017 |  |  |  |  | 16 | 18 | 20 | 17 | 0 | 0 | 85 |  | 
FORECAST 01.03.2017 |  |  |  |  | 16 | 16 | 18 | 20 | 20 | 5 | 105 |  | 
 |  |  |  | Second supplier |  |  |  |  |  |  |  |  | 
Increase in the number of modules !!
Increase in the number of modules to be produced
  9 modules for SQS rescheduled for day 1
  4 modules for XTD9
  3 modules for SPB new component (SACT)
  Modifications temporary being produced in IKC due to lack of resources in AE.

## Slide 3: Production SASE3
Chart: 
| NOV | DEC | JAN | FEB | MARCH | APR | MAY | JUNE | JULY
INITIAL FORECAST | 0 | 4 | 17 | 22 | 22 | 20
DONE | 1 | 0 | 13 | 12
FORECAST 01.03.2017 | 16 | 16 | 18 | 20 | 20 | 5
Production rate below the planning
  Lack of CRD approved in January to provide E-plan designs to two suppliers.
  Start of production with Beckhoff is being slower than expected.

## Slide 4: E-plan design SASE3
E-design SASE3 (acc. to Alfresco folder 3) |  |  |  |  |  |  |  |  |  |  | 
 | OCT | NOV | DEC | JAN | FEB | MARCH | APRIL | MAY | TOTAL |  | 
DONE | 1 | 10 | 5 | 17 | 21 |  |  |  | 54 |  | 
INITIAL FORECAST | 1 | 15 | 15 | 20 | 26 | 8 | 0 | 0 | 85 |  | 
FORECAST 01.02.2017 |  |  |  |  | 20 | 22 | 10 | 0 | 85 |  | 
FORECAST 01.03.2017 |  |  |  |  | 20 | 22 | 22 | 8 | 105 |  | 
 |  | 1st person hired | 2nd person hired | 3rd person hired |  |  |  |  |  |  | 
Chart: 
| OCT | NOV | DEC | JAN | FEB | MARCH | APRIL | MAY
INITIAL FORECAST | 1 | 15 | 15 | 20 | 26 | 8
DONE | 1 | 10 | 5 | 17 | 21
FORECAST 01.03.2017 | 20 | 22 | 22 | 8
Increase in the number of modules !!

## Slide 5: Planning overview

## Slide 6: Planning overview