## Slide 1: 73th Section Coordination Meeting XHEXP1
A. Violante (PSPO)
10.3.2017

## Slide 2: Agenda
SASE1-3 Status Updates
Beckhoff electronics – Status Report (M. Areste)

## Slide 3: SASE1-3 status update
Summarize most recent and current time-critical tasks / dates for each SASE individually.
At least weekly updated.
In Alfresco: Document Library/Planning
SASE1 Status update
SASE2 Status update
SASE3 Status update

## Slide 4: SASE1

## Slide 5: 8.2.: SPB-Experiment D.09 with curtains, first cables being pulled.

## Slide 6: 08.3.: SPB EXP D.09 - All the curtains installed, cabling continues, NKB chambers in!

## Slide 7: 08.3.: SPB OPT D.02- MKB chambers in. Mechanics being mounted in clean room conditions.

## Slide 8: From Inside D.02! Preparation of the clean tent (Courtesy of Richard Bean)

## Slide 9: From Inside D.02! Inside the boxes (Courtesy of Richard Bean)

## Slide 10: 08.03 : Interlock installations being cabled

## Slide 11: 08.03.: FXE floor being grinded – measures against dust

## Slide 12: 08.03.: SPB control room being set up (FXE as well)

## Slide 13: Phase II cabling
D.05 – FXE Exp. “Fertigmeldung„ received
XTD9 – SPB components “Fertigmeldung„ received
D.02 – SPB Opt. Final 22 (250) cables arriving next week
D.13 – SPB Laser Final 16 (130) cables arriving next week
D.09 – SPB/SFX Exp. More than 50% installed, ongoing
Wall connection boxes (D.05, D.09) arriving in KW12
 Test of the beckhoff loops by AE in FXE starting.

## Slide 14: Final acceptance tests (VOB-Abnahmen)
Dräger (Gases): VOB-Abnahme 15.2.
Jeske (Sanitary): VOB-Abnahme 13.2.
A+S (Fire saf.): Docs received and being checked.  VOB-Abnahme 15.03.
Engie (AC):
  Measurements ongoing – Curtains in D.05 to be delivered
 VOB-Abnahme ca. end of March

## Slide 15: SASE3

## Slide 16: 08.3.: SQS/SCS exp hutches - AC devices (Caverion) have arrived!

## Slide 17: 08.3.: Media installation ongoing

## Slide 18: 08.03.: LaserMet started pulling the laser Interlock cables in the entire SASE3

## Slide 19: SASE2

## Slide 20: 8.2.: 2nd Crane in MID-Experiment has been installed

## Slide 21: 8.3.: Air ducts+AC devices being installed in MID Exp

## Slide 22: 8.3.: Cable trays being installed (HED Enclosure)

## Slide 23: 8.3.: Cable trays being installed (outside)

## Slide 24: Upcoming Dates & Meetings
Today, 9:00: SASE1 Readiness
17.3., 8:30: Regular TC-Meeting