## Slide 1: XGM – progress week 10 / 2017
Dr. Jan Grünert
X-ray Photon Diagnostics
Group Leader
Hamburg, March 10th, 2017
Contains information from WP74 team
and from K.Tiedtke / F.Jastrow from DESY-FS-FL-D

## Slide 2: XGM - Progress (w10)
XGM@XTD2
  ADAM&Femto crate installed
XGM@XTD9
  ADAM&FEMTO crate installed
  Installation of signal cables and local cables on chambers: DONE
  Cabling installed for XGM-vacuum-to-Beckhoff (but not yet “plugged in”)
  Survey&Alignment: DONE / OK
XGM@XTD10
  Electronics crates (MTCA and HV crate) installed and wired to network
  Survey&Alignment: DONE / OK
XGM gas supply
  Installed bottles in gas cabinet XS3-UG1: B50 N2 200 bar, B50 Ar 200 bar, Kr 100 bar, Xe 6 bar

## Slide 3: XGM – Repair Progress Summary (w10)
XGM | Preparation | Resistor exchange | Leak test | HV test | Survey
HERA XGM01 | done | done | done |  | 
XTD2 XGM02 | done | done | done | done | done
XTD9 XGM04 | done | done | done | done | done
XTD10 XGM07 | done | done | done |  | done*
XHE3 XGM05 |  |  |  |  | 
XHE3 XGM06 |  |  |  |  | 

## Slide 4: Grounding of XGMs
Grounding recommendations by DESY: Peter Göttlicher, Narcisse Ngada, Fini Jastrow

## Slide 5: XGM - Plan week 11
Planning of Next Repairs and Grounding Works
  Installation of cable connection Girder   ADAM&FEMTO crate in XTD2+9
XGM@XTD9
  Finalize XGM-vacuum-to-Beckhoff wiring probably on 9.3.2017
  Local VAC Beckhoff test next week (w11)
XGM@XTD2
  Commissioning of all slow DOOCS controls (Keithleys, SRG, HV, RVC, ADAMs, FEMTOs)
XGM@XTD10
  Start of cabling work
This will mark the end of XGM cabling work in SASE1 !