## Slide 1: XGM – progress week 13 / 2017
Dr. Jan Grünert
X-ray Photon Diagnostics
Group Leader
Hamburg, March 31st, 2017
Contains information from WP74 team
and from K.Tiedtke / F.Jastrow from DESY-FS-FL-D

## Slide 2: XGM - Progress (w13)
XGM@XTD2
  Grounding works performed and completed
XGM@XTD9
  SRG RD calibration measurement done (for N2)
  Serial connection from MTCA to RVC 300
XGM@XHE3
  Repair (exchange of resistors) of XGM005 and XGM006
  Free up our UPS at XHE3 to install it at XGM@XTD10
  Grounding works planning for XTD9+10 on Friday 31.3.2017
Commissioning of all DOOCS controls (incl. ADAM&FEMTO) at XTD2+9: DONE

## Slide 3: DOOCS control panels operating

## Slide 4: XGM – Repair Progress Summary (w13)
XGM | Preparation | Resistor exchange | Leak test | HV test | Survey
HERA XGM01 | done | done | done |  | 25.4.2017
XTD2 XGM02 | done | done | done | done | done
XTD9 XGM04 | done | done | done | done | done
XTD10 XGM07 | done | done | done | done | done
XHE3 XGM05 | done | done |  |  | 
XHE3 XGM06 | done | done |  |  | 

## Slide 5: XGM - Plan week 14
Grounding works
  continue with XTD9 + XTD10
XTD 2:
  Serial connection from Beckhoff to TCP 350.
  Change remaining cold plug cables into halogenfree cables.
  insert XGM-vacuum into LOOP
XTD 9:
  INHIBIT connection Iseg HV crate.
XTD 10:
  Vacuum part and Gas Panel wiring of XGM – ongoing
  Installation of UPS
  Local wiring on XGM chambers; installation ADAM & Femto crate

## Slide 6: MCP - status
MCP@XTD2: detected big issue with downstream manipulator during Technical Commissioning:
  Mechanical failure of spindle, friction up to seizure
  Must be replaced, cannot be done in-situ
Repair Status: DONE
  Opened UHV, removed delicate MCPs
  Remove + repair manipulator at VAb DONE (w12)
  Reinstallation DONE (w13)
  Recommissioning: HV conditioning
  Checking MCP-BOS: OK
MCP s/w commissioning (Beckhoff):
  Motor movement using mc2lib / Technosoft controller locally tested, to put in LOOP by AE (end of w13?)
MCP s/w commissioning (karabo):
  ongoing (with CY,WE) today 9am at XTD2