## Slide 1: EAC planning SASE1
Notes: How to edit the title slide
Upper area: Title of your talk, max. 2 rows of the defined size (55 pt)
Lower area (subtitle): Conference/meeting/workshop, location, date, your name and affiliation, max. 4 rows of the defined size (32 pt)

## Slide 2: Planning 02-02-2017
Dates for firmware 02-02-2017:
  FXE: 15.03.2017 / SPB: 27.04.2017
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
Close Master View

## Slide 3: Initial assumptions
Initial assumption were:
  AE, CAS and EET had the tunnel as first priority but could dedicated some resources to keep working in the Instrument’s firmware.
  Mid of March task force in the tunnel would be almost finished and the resources for instruments would increase.
Notes: Copy & paste an element from the Clip Board to the particular slide: 1. Click on a box to mark it.
2. Position the mouse pointer on the box frame: Copy! 3. Click on the particular slide: Paste!
How you intend to use the elements is your choice. You can combine the text block style with the background colour in different manner.
Insert a new slide: Home > “New Slide” and choose either "Title slide", "Title and content",
"Title only", or "No title and content". Default is "Title and content".

## Slide 4: New assumptions
  April  still limited resources available, 4 loops/month
    FXE: loops from 1 to 4.
  May  Increase rate to 6 loops/month
    FXE: loops from 5 to 8
    SPB Optical hutch: loops 1 and 2
  June & July  6 loops/month
    SPB: loops from 3 to 14
  This planning is driven by the availability of AE resources

## Slide 5: Planning SASE1
FXE
SPB Opt. hutch
SPB
Notes: Before you start editing the slides of your talk change to the Master Slide view:
Menu button “View” > Slide Master:
Edit the following items:
1. On the Title slide (second master slide)
a) Click to add title of your talk
b) Click to add subtitle (conference, location, name of the speaker, date)
2. On the Slide Master (first master slide)
a) The 1st row in the violet header: Delete the existent text and write the title of your talk into this text field b) The 2 rows in the footer area: Delete the text and write the information regarding your talk (same as on the Title Slide) into this text field.
Close Master View