## Components-by-priority
Status: | 16/02/2017; 12:52
Completion dates
FXE/LPD1M | Device | Priority* | Coor. Person | Mechanics by/when | Cables, Elec-HW, Doc by/when | Beckhoff fw by AE/when | Ctrl-sw by CAS/when | SW by WP75 Side/when | Techn. comm. by WP75 by/when | Comments Assumption Exclusive Implementation (AGIPD or LPD)
HERA South | AGIPD/Cooling System | High | Sztuk-Dambietz | done | done | done | done | w19 | w19 | Macros and ramping functions need to be implemented and tested. Depends on CAS SQUAD.
HERA South | AGIPD/Vacuum System | High | Sztuk-Dambietz | done | done | done | done | w25 | w25 | Macros and ramping functions need to be implemented and tested. Depends on CAS SQUAD.
HERA South | AGIPD/Cables + Power Supplies | High | Sztuk-Dambietz | done | done | done | Part. Done | See commment for Control System | See comment | Reset of HV ISEG power supply, GUI missing and macros missing, Depends on CAS SQUAD.
HERA South | AGIPD/Detector Control System | High | Hauf | Not Applicable | done | Not Applicable | w20 | See commment | w20 | WP75 can provide software part if CAS provides all required framework functionality; Master FPGA and PLC is not operational.
HERA South | AGIPD/Detector Safety System | High | Sztuk-Dambietz | Not Applicable | done | w19 | w20 | w20 | w21 | Presently under test. Interlock thresholds not propperly considered. No documentation of CAS the low devices available. Middle layer devices missing. Depends on CAS SQUAD. Assumes that AE is not defocussed from our tasks.
HERA South | AGIPD/Quadrant Motion System | High | Sztuk-Dambietz | Not Applicable | [5 empty] | Motion system not expected to be operational before mid of April, hardware issues to be solved by AGIPD collaboration
HERA South | AGIPD/Clock & Control System | High | AE | Not Applicable | done | Not Applicable |  | done | done | Karabo V2.x devices are missing. Depends on CAS SQUAD.
HERA South | AGIPD/Alignment | Low | Hauf | Not Applicable | Not Applicable | Not Applicable | Not Applicable | w26 | w27 | Tech. comm. depends on availabiltiy of X-ray beem at beam line
HERA South | AGIPD/DAQ and Datamanagement | High | ITDM | Not Applicable | done | Not Applicable | done | w22 | w22 | Run management system required from CAS/ ITDM+update to Karabo 2.x; data taking possible up to cache, no writing yet
HERA South | AGIPD/Calibration Software | High | Hauf | Not Applicable | Not Applicable | Not Applicable | done | w23 | w23 | If no changes are made on CAS side Ctr-sw part done, otherwise upgrade on WP75 side required; Software for AGIPD needs to be ported to XFEL library. Time line assumes AGIPD gets priority now.
HERA South | AGIPD/Performance without X-rays | Medium | Sztuk-Dambietz | Not Applicable | Not Applicable | Not Applicable | done | w24 | w25 | Algorithms exist, macro implementation + definition outstanding
HERA South | AGIPD/Performance with X-rays | Medium | Sztuk-Dambietz | Not Applicable | Not Applicable | Not Applicable | done | w25 | w27
HERA South | LPD/Cooling System | High | Lang | done | done | Not Applicable | Not Applicable | Not Applicable | done
HERA South | LPD/Cables + Power Supplies | High | Lang | Not Applicable | done | Not Applicable | done | done | done
HERA South | LPD/Detector Control System | High | Hauf | Not Applicable | Not Applicable | Not Applicable | w19 | w19 | w19 | Delayed since Karabo2.1.8/ 2.1.9 release delayed by one week. Still not all features are included (e.g. spark lines).
HERA South | LPD/Detector Safety System | High | Lang | Not Applicable | done | Not Applicable | Not Applicable | Not Applicable | done
HERA South | LPD/Quadrant Motion System | High | Lang | done | done | Not Applicable | done | Not Applicable | done
HERA South | LPD/Clock & Control System | High | AE | Not Applicable | done | Not Applicable |  | done | ?? | Karabo V2.x devices are missing. Depends on CAS SQUAD.
HERA South | LPD/Alignment | Low | Lang | Not Applicable | Not Applicable | Not Applicable | Not Applicable | w26 | w27 | Tech. Comm. Depends on availabiltiy of X-ray beem at beam line
HERA South | LPD/DAQ and Datamanagement | High | ITDM | Not Applicable | done | Not Applicable | done | done | w19 | Run management system required from CAS/ ITDM+update to Karabo 2.x; data taking possible up to cache, no writing yet. Full speed DAQ to disk not possible at the moment due to throughput limitations.
HERA South | LPD/Calibration Software | High | Hauf | Not Applicable | Not Applicable | Not Applicable | done | done | w19 | If no changes are made on CAS side Ctr-SW part done, otherwise upgrade on WP75 side required;
HERA South | LPD/Performance without X-rays | Medium | Lang | Not Applicable | Not Applicable | Not Applicable | done | w20 | w23 | Algorithms exist, additional macros to be implementation + definition outstanding
HERA South | LPD/Performance with X-rays | Medium | Lang | Not Applicable | Not Applicable | Not Applicable | done | w22 | w27 | Algorithms exist, additional macros to be implementation + definition outstanding
HERA South | Train Builder Device | High | AE | Not Applicable | Req.Doc. Done | Not Applicable | w20 | w20 | w21 | Trainbuilder is operational but needs API library from RAL, Karabo implementation is missing. Depends on CAS.