## Components-by-priority
Status: | 1/06/2017; 15:00
Completion dates
FXE/LPD1M | Device | Priority* | Coor. Person | Mechanics by/when | Cables, Elec-HW, Doc by/when | Beckhoff fw by AE/when | Ctrl-sw by CAS/when | SW by WP75 Side/when | Techn. comm. by WP75 by/when | Comments Assumption Exclusive Implementation (AGIPD or LPD)
HERA South | AGIPD/Cooling System |  | Sztuk-Dambietz | Done | Done | Done | Done | Done | Done
HERA South | AGIPD/Vacuum System | High | Sztuk-Dambietz | Done | Done | Done | Done | w25 | w25 | Macros for pumping and venting need to be implemented and tested. Not critical.
HERA South | AGIPD/Cables + Power Supplies | High | Sztuk-Dambietz | Done | Done | Done | Done | w23 | w23 | Frist version of power procedure implemented and tested at HERA South. Some problems were discovered. The procedure has to be retested after bug fix.
HERA South | AGIPD/Detector Control System | High | Hauf | Not Applicable | Done | Not Applicable | w24 | w24 | w24 | Tests of updated (after the AGIPD squad) MFPGA and MC control software done to the level which does not require full DAQ system.
HERA South | AGIPD/Detector Safety System | High | Sztuk-Dambietz | Not Applicable | Done | Done | w23 | w23 | w23 | Presently under test. Interlock issues in PLC firmware were fixed. Middle layer devices missing. Assumes that AE is not defocused from our tasks.
HERA South | AGIPD/Quadrant Motion System |  | Sztuk-Dambietz | Not Applicable | [5 empty] | Motion system (hardware was upgraded. To be tested, not on high priority at the movement
HERA South | AGIPD/Clock & Control System | High | AE | Not Applicable | Done | Not Applicable | requested follow-ups pending | Done | ?? | Initial device tested and commissioned button-expert device requested from CAS
HERA South | AGIPD/Alignment | Low | Hauf | Not Applicable | Not Applicable | Not Applicable | Not Applicable | w26 | w27 | Tech. comm. depends on availability of X-ray beem at beam line
HERA South | AGIPD/DAQ and Datamanagement | High | ITDM | Not Applicable | Done | Not Applicable | Done | w23 | w24 | Wiring of TB to PC layer has to be done by AE/ITDM. Configuration of PC layer and 1Mpix TB for AGIPD has to be done by ITDM/AE respectively
HERA South | AGIPD/Calibration Software | High | Hauf | Not Applicable | Not Applicable | Not Applicable | Done | w25 | w25 | If no changes are made on CAS side Ctr-sw part done, otherwise upgrade on WP75 side required; Software for AGIPD needs to be ported to XFEL library. Time line adjusted to LPD priority
HERA South | AGIPD/Performance without X-rays | Medium | Sztuk-Dambietz | Not Applicable | Not Applicable | Not Applicable | Done | w26 | w27 | Algorithms exist, macro implementation + definition outstanding
HERA South | AGIPD/Performance with X-rays | Medium | Sztuk-Dambietz | Not Applicable | Not Applicable | Not Applicable | Done | w28 | w29
HERA South | LPD/Cooling System |  | Lang | Done | Done | Not Applicable | Not Applicable | Not Applicable | Done
HERA South | LPD/Cables + Power Supplies |  | Lang | Not Applicable | Done | Not Applicable | Done | Done | Done
HERA South | LPD/Detector Control System |  | Hauf | Not Applicable | Not Applicable | Not Applicable | Done | Done | Done
HERA South | LPD/Detector Safety System |  | Lang | Not Applicable | Done | Not Applicable | Not Applicable | Not Applicable | Done
HERA South | LPD/Quadrant Motion System |  | Lang | Done | Done | Not Applicable | Done | Not Applicable | Done
HERA South | LPD/Clock & Control System |  | AE | Not Applicable | Done | Not Applicable |  | Done | Done | Potentially user-friendly middle layer device needed on top
HERA South | LPD/Alignment | Low | Lang | Not Applicable | Not Applicable | Not Applicable | Not Applicable | w26 | w25 | Tech. Comm. Depends on availabiltiy of X-ray beam at beam line, photographic technique making good progress - tested on quadrant system
HERA South | LPD/DAQ and Datamanagement | High | ITDM | Not Applicable | Done | Not Applicable | Done | Done | w22 | Basically functional, long run tests delayed because of problems with TB and CC, reader service not yet ready by ITDM, no metadata catalogue
HERA South | LPD/Calibration Software | High | Hauf | Not Applicable | Not Applicable | Not Applicable | Done | Done | w23 | Charge injection devices currently in commissioning
HERA South | LPD/Performance without X-rays | Medium | Lang | Not Applicable | Not Applicable | Not Applicable | Done | w22 | w25 | Algorithms exist, additional macros to be implemented + definition outstanding
HERA South | LPD/Performance with X-rays | Medium | Lang | Not Applicable | Not Applicable | Not Applicable | Done | w22 | w23 | X-ray tests will be shortened to one week to check basic functionality and comparison with charge injection data
HERA South | Train Builder Device | High | AE | Not Applicable | Req.Doc. Done | Not Applicable | w25 | w25 | w25 | Trainbuilder is operational, first iteration for Karabo device delivered to CAS, but needs updates/improvements