### 2. ATCA demonstration in September 2009 with DESY ATCA carrier board version 2

#### Goals

Demonstration at FLASH of an almost complete ATCA-based LLRF system for XFEL. The benefits of the demonstration will be:

- evaluation of hardware,

- identification of missing hardware components, links, functionality

- evaluation of communication links throughput, computation power required, bottlenecks,

#### Hardware Setup

Error creating thumbnail: /srv/www/htdocs/wiki/bin/ulimit-tvf.sh: line 5: 28610 File size limit exceeded"$@"

Hardware Block Diagram for Tests in September 2009

- ATCA Shelf with Shelf Manager

- 4 DESY carriers including:

  - 1 carrier with 3 TAMC900 for 24 probes

  - 1 carrier with 3 TAMC900 for 24 forward power

  - 1 carrier with 3 TAMC900 for 24 reflected power

  - 1 carrier for TAMC900, AMC-TIM and AMC-VM

- 10 TEWS TAMC900 - for usage see previous point

- 10 Cryoelectra DWC on 4 RTM modules for 4 carrier boards

- AMC-VM

- AMC-TIM - timing module

- ADlink CPU 6900 – with PCIe riser card for RC, DOOCS servers, etc.

- ATS1936 – for switching Ethernet on the backplane

#### Schedule

| Hardware Milestone | Date |  | Date | Software Mileston |
| --- | --- | --- | --- | --- |
|  |  |  | 05.03.2009 | Downconversion and readout of 8 channels from RTM through carrier in TAMC900 Performance evaluation |
| Carrier #2 and #3 produced | 16.03.2009 |  |  |  |
|  |  |  | 23.03.2009 | 1. Tests in Lodz of IPMI and PCIe with Carrier #1 2. Tests of LLL and RocketIO between 2 carriers and AMC at DESY |
| Finished debugging of critical elements for ATCA Demo on the DESY Carrier | 01.04.2009 |  | 01.04.2009 | Firmware on Spartan for configuration of DSP and FPGAs on AMC and Carrier |
|  |  |  | 22.04.2009 | Tests of communication links between FPGA and DSP on the carrier |
| 1. Zone 3 Backplane ready to use 2. 5 additional AMC-B modules produced | 01.05.2009 |  | 01.05.2009 | AMC-TIM assembled and installed in carrier - tests of firmware and DOOCS server |
|  |  |  | 15.05.2009 | 1. 3 Carrier boards, 3 RTMs and 3 TAMC900 assembled in laboratory - tests of IPMI and JTAG configuration 2. Tests of external triggers and clocks with Z3 Backplane 3. AMC-VM and AMC-TIM installed and tests of the firmware |
| Production of DESY carrier boards #4, #5 (#6) | 01.06.2009 |  | 01.06.2009 | DOOCS server for AMC-VM - configuration of AMC-VM features |
| Purchasing of 7 TAMC900 modules | 01.06.2009 |  | 01.06.2009 | Tests of LLRF controller with 3 TAMC900, AMC-VM and 2 carrier boards |
|  |  |  | 15.06.2009 | 1. Installation of complete system in laboratory - tests of IPMI, JTAG configuration, communication links 3. Tests of DOOCS server for the LLRF controller |
| Demonstration of the complete system in laboratory (including software) | 30.06.2009 |  | 30.06.2009 | 1. Identification of weak points and missing elements 2. Schedule preparation for improvement and installation in Extension Hall |
| Demonstration of the complete system in ACC456 | 15.09.2009 |  |  |  |

[edit]

#### Software Tasks

- System components for ATCA carrier (based on DESY Carrier V2)

  - IPMC on the carrier

  - VHDL firmware for Spartan

  - VHDL component for external memory

  - VHDL component for Ethernet to Base Interface

  - Linux kernel for PowerQUICC – for V3

  - Drivers for PCIe on ADlink CPU-6900

  - Configuration of Ethernet switch on the carrier – for V3

  - Front-end servers – DOOCS or TINE (DOOCS with ADlink 6900)

  - Part of the distributed LLRF controller which includes all algorithms implemented so far

  - DOOCS server or/and front-end server for distributed controller

  - VHDL firmware for LLL (AMC-Carrier, Carrier-Carrier)

- Software for TAMC900:

  - VHDL for TAMC900 – IQ detection, partial vector sum – part of the distributed LLRF controller

  - VHDL component for external memory

  - VHDL full speed DAQ through PCIe

- Software for AMC-B

  - MMC

- Software for timing module

  - VHDL firmware on AMC-B for timing configuration

  - DOOCS server

- Software for vector modulator

  - VHDL firmware for AMC-VM configuration

  - VHDL part of the distributed LLRF controller

- Software AMC communication module (what module??? – optical links for LLL, Ethernet)

  - Communication in distributed system – LLL, Ethernet

  - Communication with piezo drivers

  - Communication with beam based feedback

- Configuration of Diversified Technology ATS1936 Ethernet switch

- DOOCS panels for ATCA 5-slot management based on IPMI-DOOCS server

- DOOCS server(s) for ATCA system including firmware on:

  - 10xTAMC900 - readout of signals from all ADCs, configuration of IQ detectors and partial VM

  - AMC-VM - configuration of AMC-VM parameters, configuration of the firmware for DAC control, diagnostic

  - AMV-TIM - configuration of the AMC-TIM parameters, control of the signals generation, diagnostic and 4 carrier boards

  - server for LLRF controller on one of the carrier boards

  - optionally server for LLA on 3 other carrier boards for Z. Geng