## Slide 1: Schedule and Priorities 2018 / 2019

## Slide 2: Current 2018 schedule

## Slide 3: Scope 2018/19 / Order of priorities
SASE1 tunnel operation
SASE1 instrument operation
SASE3 tunnel readiness  SASE3 tunnel operation
SASE2 tunnel readiness  SASE2 tunnel operation
SASE3 instrument readiness  SASE3 instr. operation
SASE2 instrument readiness  SASE2 instr. Operation
SASE1 tunnel & instrument completion
SASE3 tunnel & instrument completion
SASE2 tunnel & instrument completion

## Slide 4: 1. SASE1 tunnel operation
Tasks & effort required to operate the tunnel: (including items for Day-1 or required to meet promises in Call for Proposals)
  Accelerator: Achieve >0.5 mJ and good pointing stability (matching our optics)
  Accelerator / XFEL: Improve undulator controls & adjustments / reduce losses
  Accelerator: Good understanding of the FEL gain curve (?)
  Accelerator: Working kicker magnets
  Accelerator / Diagnostics: Measurement of the spectral jitter and bandwidth
  Optics: Installation & commissioning of distribution mirror cooling
  Diagnostics Complete commissioning of MCP, Hirex, K-Mono (now 50%) (required for improvements of the accelerator)
  CAS & ITDM: Tunnel DAQ reliability / commissioning
  Vaccuum & CAS: Final implementation of vacuum controls.
  FXE: Installation & commissioning of diamond grating
  FXE: Commissioning of 4 bounce monochromator
  AE & SPB: Pulse picker has to be comissioned with beam
  SPB: Update attenuator foils

## Slide 5: 2. SASE1 instrument operation
Tasks & efforts required to operate the instruments: (including items for Day-1 or required to meet promises in Call for Proposals)
  October:
    SPB: AGIPD (re)cabling works done, CSS, laser table & vacuum works partially done, …
    CAS: Exchange of data between DOOCS and Karabo: Established, currently testing and bugfixing.
    CAS: Improve Control Software: Scan tool being tested @ FXE, overall stability was increased.
    ITDM: Improve DAQ: Data storage and handling, detector performance waiting for opportunity to conduct high speed test (300/512 bunches)
  December:
    ITDM: Test of new storage system + expansion of InfiniBand network
    AE: Test of train builder (at least LPD)
    Accelerator & SPB/SFX: Improvement of the focal properties
  From beginning of 2018:
    SPB: KB-mirror installation, integration & commissioning

## Slide 6: 3. SASE3 tunnel readiness
Achieve first lasing: 1st attempt in Nov. 17  Q1 2018
  Diagnostics: XGM, FEL- & SR-Imager are (almost) ready for commissioning
  Vacuum: Vacuum in XTD10 up to absorber completely done
  Vacuum: Local test of vacuum system with controls, interlock etc. done General vacuum sector interlock test has still to be done
Major works finished XTD4+10 : End of Jan. 18
  Vacuum & Optics: Beam shutters, mirrors, soft X-ray Monochromators cabling was already started
  Diagnostics: MCP (30% inst. done), Pop-Ins, K-Mono (50%)
Simultaneous operation of SASE1+3: End of Q1 2018
  To be discussed with Acc. and incorporated into schedule

## Slide 7: 4. SASE2 tunnel readiness
Achieve first lasing: 1st attempt in Mar. 18  Apr.-May
  Beam shutters, XGM, FEL-&SR-Imager, Vacuum in XTD1+6 up to XTD6 absorber
  Test of entire vacuum system, with controls, interlock etc. required
Major works finished XTD1+6: Apr. 18  End of Q2 2018
  Vacuum & Optics: Mirrors, Split&Delay Unit, High resolution monochromator, CRLs
  Diagnostics: 2nd XGM, MCP, Pop-Ins and other Imagers
Simultaneous operation of SASE1+3+2: End of Q2 2018
  To be discussed with Acc. and incorporated into schedule

## Slide 8: 5. SASE3 instrument readiness
TGA
  AC ready until Feb. / Apr. 18, Elec. ready until Mar. 18
Instrument installation
  Major time of installation: Feb. – Apr. 18
Beckhoff electronics
  Cabling Phase II done until Jan.18
  Day 1 hardware BH done until Feb. 18
  Beckhoff electronics E2E done until Jul. 18
Instrument commissioning without beam
  Installation of Rad. Saf. Interlocks in Apr. 18
  …

## Slide 9: 6. SASE2 instrument readiness
TGA
  AC ready until Mar. / Apr. 18, Electricity ready until Apr. 18
Instrument installation
  Major time of installation: Q4 2017 - Q1 2018
  AGIPD ready for installation in Feb. 18
Beckhoff electronics (MID / HED Opt. / HED)
  Cabling Phase II done until May / July / Sep. 18
  Day 1 hardware BH done until Feb. / Mar. / June 18
  Beckhoff electronics E2E done until Sep. 18 / Oct. 18 / Jan. 19
Instrument commissioning without beam
  Installation of Rad. Saf. Interlocks in July 18
  Installation of Laser Interlocks ???

## Slide 10: 7. SASE1 tunnel & instrument completion
Tunnel:
  …
FXE:
  Jungfrau detector planning, cabling, integration & commissioning
  …
SPB/SFX:
  Jungfrau detector planning, cabling, integration & commissioning
  AGIPD4M detector planning, cabling, integration & commissioning
  Additional work regarding downstream region (day 2 / SFX)
  …

## Slide 11: 8. SASE3 tunnel & instrument completion
Tunnel:
  Undulators: Self-seeding, Circular polarization undulator, Helical afterburner
  Diagnostics: Full PES operation, Exit-Slit Imagers
  …
SCS:
  …
SQS:
  …
Third experiment (TR-XPES):
  …

## Slide 12: 9. SASE2 tunnel & instrument completion
Tunnel:
  Undulators: Self-seeding, …
  Diagnostics: Hirex?
  …
MID:
  …
HED / HIBEF-UC:
  …
(Third experiment:)
  …