## Explanations
Explanations of applied modifications
Rev. 2 | ● | Added weeks for X-ray commissioning [XC]: Operation of ACC, X-ray BT, XP, Instruments in conditions 'identical' to following user exp
| ● | Did not significantly touch AD and XD times, neither shutdowns
| > | reserve' time 2017 extends until summer shutdown
| > | beamtime for 2nd EUE allocation only after summer shutdown
| ● | starting end of Aug; total 6 wks/27 day/54 sh until end of Oct
| ● | removed short (1wk) Sep shutdown
| ● | Tried new user week model: 2d XC+4d UP (starting in Oct)
| > | beamtime for 3rd EUE allocation could (potentially) start mid Nov
| ● | total 4 wks/16 d/32 sh
| ● | to be continued in spring 2018 (until summer shutdown ?)
| > | downside: less UP time : ~ 1600 hrs
| > | AD time reduces to ~1700 hrs, but this comes largely by definition of 6 day slots for AD&XD (each 3d)

## OAO-2018-v2-DRAFT
Outline Annual Operation Schedule 2018 (rev. 2.1 - D R A F T )
[39 empty] | ST | Access, Setup, Tuning
| Legende: |  |  |  | Weekend |  |  |  | Bank holiday |  |  |  | Scheduled down |  |  |  |  | ST |  |  | AD |  |  | XD |  |  | UP/XD |  |  | XC | [8 empty] | AD | Accelerator dev.
[39 empty] | XD | X-ray Dev.
2018 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | SD | ST | AD | XD | UP/XD | XC |  | UP | User Program
Jan | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We
Mo: 1; Mo: 2; Mo: 3; Mo: 4; Mo: 5 | [7 empty] | Summer vacations:
Jan: Program | 21 | 5 | 5 | 0 | 0 | 0 | 31 | HH: 5.7. - 15.8.
Feb | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | [10 empty] | LS: 26.6. - 8.8.
Program Mo: 6; Program Mo: 7; Program Mo: 8; Program Mo: 9 | [10 empty] | SH: 9.7. - 18.8.
Program Feb: Program |  |  |  | 0 | 4 | 13 | 11 | 0 | 0 | 28
Mrz | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa
[5 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13
Program Mrz: Program | 0 | 4 | 9 | 0 | 8 | 10 | 31
Apr | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18
Program Apr: Program |  | 17 | 4 | 7 | 0 | 2 | 0 | 30
Mai | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th
[7 empty] | 18 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22
Program Mai: Program | 0 | 5 | 10 | 5 | 5 | 6 | 31
Jun | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa
|  |  |  | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26
Program Jun: Program |  | 11 | 2 | 3 | 0 | 10 | 4 | 30
Jul | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu
|  | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31
Program Jul: Program | 8 | 7 | 10 | 6 | 0 | 0 | 31
Aug | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr
[6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35
Program Aug: Program | 0 | 4 | 5 | 10 | 5 | 7 | 31
Sep | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
|  |  | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39
Program Sep: Program |  | 0 | 10 | 3 | 0 | 9 | 8 | 30
Okt | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We
| 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43 | [6 empty] | 44
Program Okt: Program | 0 | 5 | 5 | 3 | 12 | 6 | 31
Nov | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr
[5 empty] | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | 48
Program Nov: Program |  | 0 | 4 | 5 | 6 | 9 | 6 | 30
Dez | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  |  | 49 | [6 empty] | 50 | [6 empty] | 51 | [6 empty] | 52
Program Dez: Program | 22 | 1 | 0 | 0 | 6 | 2 | 31
Program Sa: Program work (course); Program Sa: Sums:; Program Mo: days | 79 | 55 | 75 | 41 | 66 | 49 |  | 365
Program Sa: Jan:; Program Tu: Acc. And XTD installation & commissioning; start-up; Program Mo: hrs | 1896 | 1320 | 1800 | 984 | 1584 | 1176 |  | 8760
Program Sa: Feb & Mar:; Program Tu: SASE3 lasing; beam transport to XHEXP; After: parallel operation SASE1 & SASE3; beam through SASE2; Program Mo: v1: | 2112 | 1224 | 2088 | 1272 | 2064
Program Sa: Mar & Apr:; Program Tu: Commissioning SASE3 (and remaining SASE1); reserve user time (2 wks/10 days/240 hrs) | [5 empty] | 6864
| Apr: |  |  | Shutdown for CS9 completion; complete SASE2; SASE2 lasing
| May & Jun: |  |  | Commissioning SASE2; after: parallel operation of N & S beamlines; 2nd reserve slot EUE (3 wks/15 d/360 hrs)
| Jun&Jul: |  |  | Shutdown for Interlock tests & MKK filter exchanges; Und gap tuning; increase bunch number
| Jul & Aug: |  |  | Commission SASE3 beam transports (mono, PES, ...); start comm. SASE3 instruments
| Aug: |  |  | Allocation 2nd EUE period starting (2d)
| Sep: |  |  | 2nd allocation EUE (3 wks/13 d/312 hrs); 7d ST buffer for eventual ACC issues
| Oct: |  |  | 1 wk for AD&XD; cont. 2nd allocation EUE (3 wks/12 d/288 hrs)
| Nov: |  |  | 2 wks for Ad&XD; Allocation 3rd EUE period starting (3 wks/9d/216 hrs)
| Dec: |  |  | 3rd EUE (2 wks/6 d/144 hrs); Shutdown

## Weekly activities
Week | Activities ACC | Duration [sh] | Activities SASE1 | Duration [sh] | Activities SASE2 | Duration [sh] | Activities SASE3 | Duration [sh]
1 | XTD |  | XTD |  | XTD1: magnet tests --> interlocked |  | XTD
2 |  |  |  |  | XTD1: magnet tests --> interlocked
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52