## Slide 1: BonnDAQ Work Packets for final Development
Florian Lütticke

## Slide 2: Current Idea for BonnDAQ
DHE
DHE
DHE
DHE
DHE
DHC
x 8
ONSEN
EVB
Express Reco
BonnDAQ
Standalone DAQ running without HLT for
  PXD Calibration data
  PXD DQM on full data (no ROI)
  measuring ROI efficiency, Slow Pion rescue
Proven useful during test beams
Currently: standard lab tool for measurements
Subset of events
HLT
Simplified

## Slide 3: Current status of BonnDAQ – Lab Version (12/2017)
CMD Client(s)
CMD Client(s)
TCP Command Server
Keyboard Command Decoder
Statistics/ Health
Thread
Data structure
Read/React
Write/Control
DHE/DHC Receiver Thread
Data Distribu-tion Server
File Writer Thread
Buffer 1
Buffer 2
Read/React
Control
Socket
DHE/DHC
Listener
Listener
Data listener(s)
Error log file
File
CMD Client(s)
Compression thread pool
Data File
Compression thread pool
Compression thread pool
Main Thread
dh<x>_receiver.cpp

## Slide 4: BonnDAQ for Belle II – integrated threads
DHE/DHC Receiver Thread
Buffer 1
DHE/DHC
Error log file
DHE/DHC Receiver Thread
Buffer 1
DHE/DHC
Error log file
Create multiple DH<x> threads and build events
Easy to control, one file for all data, full online events.
Needs powerfull machine
TCP Command Server
Keyboard Command Decoder
Statistics/ Health
DHE/DHC Receiver Thread
Data Distribu-tion Server
File Writer Thread
Buffer 1
Buffer 3
Control
DHE/DHC
Data listener(s)
Error log file
CMD Client(s)
Compression thread pool
Data File
Compression thread pool
Compression thread pool
BonnDAQ instance
Event building and sorting
Buffer 2

## Slide 5: More than just a DAQ
CS-Studio GUI
DAQ Health and Status
EPICs Server,
CMD client
DHE/DHC
DHE/DHC
DHE/DHC
DQM
EPICs Server,
Data listener
DQM
EPICs Server,
Data listener
DQM
EPICs Server,
Data listener
DQM
EPICs Server,
Data listener
BonnDAQ
Measurement Script
Uses pyDepfetReader.TCPReader for data subscripton
Uses pyDepfetReader.FileReader for Analysis
Communicates with BonnDAQ
Communicates with BonnDAQ
Development for
Phase 2 and Phase 3
Maintain
compatibility

## Slide 6: Current development status
Mandatory (or done)
Port to newer threading model Done!
Develop tools for test bench Done!
Create event builder for multi DHC events
Create new file format: supports large events, has less overhead
Implement live data support for multi DHC events
Implement support for new format in pyDepfetReader
Optional:
(fix) Data compression (currently switched off)
Performance tests and optimizations

## Slide 7: Cost estimates
BonnDAQ is mission critical.
  We need a backup system!
Phase 2 Server
  (Doubles as Phase 3 Backup)
  8 Core Server
  32-64GB RAM
  8x 1 Gbit Ethernet ports
  From Dell: 4000 Euro
  Homemade: 2000 Euro
Phase 3 Solution
  24-32 Core Server
  64GB RAM
  8x 1 Gbit Ethernet port
  7000-10000 €
We need information if we can use KEK Storage!

## Slide 8: Conclusion
Unified BonnDAQ already needed for Phase 2.
Development currently on hold. I will continue after my thesis defense, but that is more important to me right now.
Time estimate: Mid to End of Feb, 2018.
Components for a self-made server selected. Need to be ordered to Japan.
We need information if we can use KEK Storage!

## Slide 9: Thank You

## Slide 10: BonnDAQ: EPICS Integration status
DAQ Health module (python + CS-Studio)
  Shows status of threads, filename, file size, connected clients (for live data), buffer fill status, error counts etc.
  Creates EPICs server, requests DAQ status and publishes EPICS variables.
  OPI display available
  Used in testbeams
Trigger mismatch display bad
Start/Stop buttons sometimes crash.
Stability testing needed
Sometimes does not reconnect when BonnDAQ is restarted

## Slide 11: BonnDAQ: EPICS Integration status
DQM display (python + CS-Studio)
  Uses pyDepfetReader.TcpReader
  Gets live data and calculates hit map, Seed/Cluster histogram, pixel occupancy histogram, common mode histogram, event size histogram
  Creates EPICs server and publishes results
  OPI display available
  Used in testbeams
  ~500 frames/sec
    two PXD modules, single thread
    ~25 frames/sec for 40 modules
Currently can only handle 1 DHC (5 DHEs)
OPI Display has hardcoded DHE IDs
Clustering only in space not in time.
Single threaded

## Slide 12: Development Work Packets

## Slide 13: Work packets
Port from pthread
Develop new File format
  Basic
  Efficient
Develop event building thread
Implement group event support in data distribution thread
Performance Fixes:
  Use Buffers
  Unwrapping UDP in Userspace
Compression
  Port to new BLOSC version
  Implement faster compression
Develop test bench

## Slide 14: Port from pthread to native c++11 thread/mutex
Current way of starting multiple threads not scalable
Pthread is not portable
C++11 threads and mutexes have a much nicer interface
  Remove startup variables form shared variables. This separates inter-thread communication from non-critical variables.
Time estimate: 2+ 1(testing) days.
Current status: finished, tested and pushed to master
Priority: Recommended

## Slide 15: Develop new file format - basic
Current file format supports only up to 4MByte/event, we need up to 8MByte/event.
Expand to 16MByte/event
Idea: Single DH<x> are stored as sub-events in a event group
Store each single DH<x> frame as header + data
Time estimate: 2+ 2(testing) days.
Current status: not started
Priority: Critical for Phase 3, optional for Phase 2

## Slide 16: Develop new file format - efficient
Create more efficient data format
Use one TOC per event instead of header+data sequence
Check data and remove redundant information if everything is ok:
  Remove CRC checksum on each frame and replace by one global checksum
  Remove end of event frame (implicitly given)
  Remove redundant parts of DH<x> frame (trigger, DHE ID…)
Time estimate: 0.5(research) +2 + 2(testing ) days.
Current status: started, 1 day in
Priority: optional

## Slide 17: Develop event building thread
Gather data from single DH<x> receiver threads
Built event groups from these.
Time estimate: 2 + 1(testing + debug) days.
Current status: 1 day in,
Priority: critical

## Slide 18: Implement group event support in data distribution thread
Basic support – client can receive full events
Time estimate: 0.25 + 0.25(testing) days.
Current status: not started
Priority: Critical
Full support – client can select sub-event
Time estimate: 1 + 1(testing) days.
Current status: not started
Priority: optional

## Slide 19: Performance – use buffers
Faster receiving and no dynamic memory allocation.
  First gather all (UDP) frames and then write event at once
Complete rewrite of receiver and event checking needed
Time estimate: 4 + 2(testing) days.
Current status: not started
Priority: optional, but now would be best time. When starting data

## Slide 20: Performance – Unwrapping UDP in Userspace
Don’t let linux kernel handle hardware but do it in BonnDAQ.
  Massive performance improvements possible
  Much better scaling when using several connections
Time estimate: unknown.
Current status: not started
Priority: please don’t

## Slide 21: Performance – other
Check NUMA, fix thread to core associativity
  Quite large improvement in cache locality possible
Time estimate: unknown. Implementation rather short.
Current status: not started
Priority: please don’t.

## Slide 22: Compression: Port to new BLOSC
Implement new BLOSC version which supports faster context switches and compression with more cores.
Needed for new compression algorithm zStandard.
Time estimate:
  Porting is rather fast but breaks backward compatibility. 2+1 days
  Creating a backward compatible solution: 5+3 days.
Current status: not started
Priority: optional

## Slide 23: Develop test bench
Develop DH<x> simulation
  Time estimate: 1 + .5(testing) days.
  Done
Develop raw data reader (like pyDEPFET reader but w/o interpretation)
  Time estimate: .5 + .25(testing) days.
  Done
Implement tests
  Time estimate: 1 + .5(testing) days
  Basic tests developed, already found an old bug 
Current status: Infrastructure there, further tests tbd.
Priority: recommended

## Slide 24: File format
Event header
Seqeuence of packets:
  128bit Header (with size)
  Payload package
Event header
Table of contents TOC
  Number of packets, type of TOC.
  List of frame sizes
List of Payloads.

## Slide 25: Cost estimates
Cost estimate:
  Buying complete server is considerably more expensive.
Phase 2 Solution
  (Doubles as Phase 3 Backup)
  8 Core Server
  32-64GB RAM
  8x 1 Gbit Ethernet ports
  From Dell: 4000 Euro
  Homemade: 2000 Euro
Phase 3 Solution
  24-32 Core Server
  64GB RAM
  8x 1 Gbit Ethernet port
  7000-10000 €
We need information if we can use KEK Storage!

## Slide 26: Data Reduction summary
Data per Scan
Reduction | None | Medium | Strong | Very Strong
Pedestal | 7.5 GB | 0.4 GB | 0.14GB | 0.008GB
Offset | 400 GB | ~115GB | 20GB | ~ 5 GB
Delays | 10 GB (0.1GB) | 0.01 GB | - | 0.0001GB
ADC curve * | 80 GB (8 GB) | 0.8 GB | - | 0.01 GB
Reduction | None | Medium | Strong | Very Strong
Pedestal x 6000 | 45 TB | 2.4 TB | 0.84 TB | 0.048 TB
Offset x 400 | 160 TB | ~46TB | 8 TB | ~ 2 TB
Delays x 100 | 1 TB (0.01TB) | 0.001 TB | - | 0.00001TB
ADC curve ** | 200 TB (20 TB) | 2TB | - | 0.025 TB
Data for lifetime
* Single Setting, all ADCs
** Assuming 50 Scans during lifetime with RefIn/AmpLow, IPSource/IPSource2, 5 values for each setting (2 * 5 * 5 measurements), scan over all channels