## Open
Shut down task list
[5 empty] | Group: | TS
| Scope of work | Start | End | Contact person | Support groups involved | Comments (include priorities, dependencies…)
1 | Maintenance MCRT D.02/D.07/C.01 |  |  | Alexander Kondraschew / Christian Holz | TS | date is not fixed yet
2 | Maintenance WKT D.02 |  |  | Alexander Kondraschew / Christian Holz | TS | date is not fixed yet
3 | Maintenance Engie Dehumidifier D.07/D.13 |  |  | Alexander Kondraschew / Christian Holz | TS | date is not fixed yet
4 | construction work on the VE-water system | 2018-06-21 | 2018-06-21 | Thorsten Bartelt | TS | ca. 2 hours
5 | cleaning of the cooling water filters D.02/D.04/D.07/D.09/D.13/C.01 | 2018-06-22 | 2018-06-22 | Alexander Kondraschew / Christian Holz | TS | 30 minutes per precision-AC-System temperature in the huches can be unstable
6 | maintenance of the electric system | 2018-06-26 | 2018-06-27 | Oleg Engelmann | TS | interruptions of the power supply (lights)
7 | construction work on the drain-water-system |  |  | Christoph Stäps | TS | the water supply will be shut down for 2 days (date is not fixed yet)
8
9
10
11
12
13
14
15
16
17
18
19
20