## Slide 1: SCS
Laser in-coupling (LIN) installed at the beamline
TIM: vacuum tests in progress
Surveying and alignment of XGM and LIN (Thursday morning)
KB x-ray optics installation in mirror benders at the diamond light source by FMB this week followed by metrology of the bent mirrors in June (~3wks)

## Slide 2: SQS

## Slide 3: SASE2 XTD6

## Slide 4: Laser
SASE 3:
remaining works for complete hutch readiness are ongoing. Finalization and commissioning till end of June seems feasible.
We will start with under table control cable installations in first week of June.
SASE 2:
remaining works for complete hutch readiness are ongoing. Currently no info on finalization.
We will start with under table control cable installations in second week of June.

## Slide 5: Vacuum
crates n the racks were connected to power
M1 installation slightly delayed due to mechanical problems
HED XGM was connected to DPS
HED SDU leak test done successfully, RGA ongoing, it will be vented afterwards for accessories installation
MID imagers not ready for installation
pumpdown and leak test on several vacuum sections ongoing

## Slide 6: Optics

## Slide 7: Photon Diagnostics

## Slide 8: Advanced Electronics
SCS
Loops 1 and 2 running and currently being tested. Some problems appeared with hardware (fuses, cabling,…), we are working on solve them
Loop 3 is being prepared but we have had some issues generating it, so would be done latest by tomorrow.
SQS
Loop 1 is running
Loop 2 and 3 have all the hardware done. Waiting for generation of the project and testing of Elmo controllers
NKB works agreed for tomorrow 31.05 to test these motors and configure the Elmo controllers
SASE2
Vacuum and EPS loop currently gathering documentation in order to start to integrate them end of this week or beginning following week.

## Slide 9: ITDM

## Slide 10: Detectors

## Slide 11: CAS