## Slide 1: SCS
Progress
Alignment XGM, LIN (problem with transfercoordinates)
  for XGM problem was found,next alignment next Tuesday.
ongoing technical commissioning and testing of ALAS and DPS
KB: FMB prepared slit installation
LIN chamber: final installation onsite was prepared.
TIM further preinstallation activities
Issues:
Beam protection plates seems to be missing.
MEA2

## Slide 2: SQS
Progress
KB mirrors installed in the SQS experimental hutch
KB vessel under vacuum again
Control electronic connected and test is ongoing (loop 3)
Under table installation in SQS laser room (E06) finished
Beckhoff loops:
  Loop 3 under test
  Loop 2 to be installed and tested next.
Start of digitizer DAQ testing

## Slide 3: SASE2 XTD6

## Slide 4: Laser
SASE 2/3:
remaining infrastructure works will take at least till end of June.
under table installation (LAS) started.

## Slide 5: Vacuum
Readiness SASE2:
crates in the racks are now all connected to power
vacuum loop has been patched by AE, commissioning and test activities have started
M1 chamber is now ready for mirror installation (next week)
HED SDU: RGA shows poor results: cleaning opportunities are being discussed
MID imagers not ready for installation
Vacuum section downstream of MID CRL vented for bellow exchange

## Slide 6: Optics

## Slide 7: Photon Diagnostics

## Slide 8: Advanced Electronics
The demonstration of the co-ordinated motion was done successfully
  many stake holders participated in the demonstration
  the implementation will now be deployed to the SPB system and soon also to SCS
Integration of the CRL in XTD1 completed
A lot of patching work (PLC Loops) in SASE2 tunnels took place
  MOV loop connected on both sides (redundancy enabled and tested)
  VAC loop patched and updated

## Slide 9: ITDM
next week we want to update the network in SASE3 (exchange of transceivers)
  need to coordinate a time slot with SCS, SQS, AE, CAS and DESY Network team

## Slide 10: Detectors

## Slide 11: CAS