## Slide 1: Project status and All Hands objectives
Daniele Cesini
daniele.cesini<at>extreme-datacloud.eu

## Slide 2: Welcome to Hamburg
Thanks to DESY for hosting the meeting, in particular to Patrick and his collaborators for the organization
Agenda:
  https://indico.desy.de/indico/event/21131/timetable

## Slide 3: The Plan for the Next Months
Nov ‘17
XDC started
Kickoff@INFN
Jan ‘18
Jul ‘18
Dissemination event@IFCA
Architecture finalized
Jun ‘18
All-Hands@DESY
Sep’18
Reference Release -1
Nov ‘18
Reference Release - 2
Nov ‘19
Jan ‘20
XDC end
Functionalities and Scalability demonstrated
Pilot tb in place
Release procedures
May‘18
Project Setup
Use case definition
Architecture definition
Dissemination
Development started
Interaction with RDA and SNIA
End of Feb or beginning of Mar 2019
1st EC review
DI4R
8-11 Oct

## Slide 4: Management bodies
ELG is responsible for maintaining active relationships with the infrastructure and technology providers, discussing synergies, strategies, roadmaps and requirements workflow for the software released by the project.
CB the ultimate decision-making body of the consortium
TCB in charge of steering the technical developments of the project
PEB is responsible for the decisions affecting the project strategy, plans, delivery schedule, conflicts within the partners and risk management
It is also responsible for the quality of the project outcome.
TCB, ELG – we need to track and/or formalize their activity
EMT
SPB
https://confluence.extreme-datacloud.eu/display/XDCPROJ/EMT+-+Engineering+Management+Team
https://confluence.extreme-datacloud.eu/display/XDCPROJ/SPB+-+Service+Providers+Board

## Slide 5: WP1 – Topics for the All Hands
WP1 - Project Management (NA1)
  T1.1: Consortium coordination and Project Management
  T1.2: Financial Management
  T1.3: Project Quality Assurance and Activities Oversight
  TT1.4: Communication
Review QA metrics and KPIs
  How are we behaving?
Consortium Agreement Signature
  during the Collaboration Board
Liaisons with EOSC-Hub (in collaboration with WP3/WP2)
  We should be ready for exploitation
    What is missing? A service catalogue? A White paper?
Review expenses reporting
Start discussing the preparation of the First EC review (PM16/17)
Communication
  How to improve website updates
  Gadgets, Twitter etc..
Track WP1 activity in confluence?
  Also WP4 and WP5
Collect publications list
INDIGO review outcome analysis

## Slide 6: Recommendation to indigo follow-up projects
Major effort has been put into adequate metrics and thresholds to measure the success of use [….]. Based on this exercise the metrics itself as well as the procedure to assess the metrics should be optimised in future projects.
What is missing so far is a clear plan for uptake of the results and spread of tools and services to other research communities not involved in INDIGO or one of the upcoming projects
Work in this area (collaboration with e-infras) must be expanded to gain wider acceptance, and the EOSC-Hub is a good platform to address this
The project should pulish in gold open access journals and conferences
A comprehensive networking solution should be considered for future projects leveraging INDIGO deliverables
More extensive scalability testing should be performed to have a convincing case when interacting with other EINFRA. INDIGO will need to demonstrate that platform and framework can scale
Continue and expand on training events to promote user and community adoption
QoS standard implemented in OneData

## Slide 7: WP2 – Topics for the All Hands
WP2: New functionalities definition and Research Communities support (NA2)
  T2.1 Use Case Analysis
  T2.2 Solutions for the EOSC Data Management
  T2.3 Integration and Testing
  T2.4 Dissemination and Training
Review use case status
  Is there something important missing in their definition?
Issues in the interaction with the developers?
  Requirements passing process
Dissemination
  DEMOs
    We need one or more DEMO
      DI4R?
    Preparation of a joint use case with DEEP
  CDB
    Status review and next step, should we withdraw?
  Identify next dissemination events

## Slide 8: Dissemination events….
We attended/organized several dissemination events and technical groups…
…created a lot of expectations
We should show demos/results in the forthcoming events
https://confluence.extreme-datacloud.eu/display/XDCPROJ/Dissemination+Events

## Slide 9: WP3 – Topics for the All Hands
Release structure definition
  What will be in the release?
  Review, update and refine the list of XDC Products
Identify the final release date
  and name
Service catalogue definition for exploitation (WP1/WP2)
Software license(s) collection (with all other WPs)
Release testing plan
  Including scalability tests
Documentation
  Which is the status for all the products?
WP3: Software Lifecycle Management, Pilot Infrastructures & Exploitation (SA1)
  T3.1: Software Lifecycle Management
  T3.2: Pilot e-Infrastructures and support services
  T3.3: Exploitation

## Slide 10: WP4 – Topics for the All Hands
WP4: Orchestration and policy driven data management (JRA1)
  T4.1 Intelligent data management and data lifecycle management
  T4.2 Smart Caching
  T4.3 Data pre-processing at ingestion/Orchestrating workflows based on data
Architecture finalization
  Auth, Message Bus/Notification, etc..
Multi-system distributed storage
  Was the final architecture agreed?
    The “Sync protocol”
  Which is the status of the developments?
  What is achievable for the first release?
DEMOs preparation
  QoS + Orchestrator
  Caching with xrootd
  EOS-dCache integration?
XDC Participation in the WLCG-DOMA activities
  QoS sub-group leadership

## Slide 11: WP5 – Topics for the All Hands
Architecture finalization
  And integration with the WP4 architecture
DEMOs preparation
  Can we identify a use case that is almost ready for a DEMO with ONEDATA?
    CTA?
    LIFEWATCH?
  One-to-one meetings with the User communities
Need to track the work done and results in one of XDC document repo
  Confluence?
WP5: Unified cross federations data management (JRA2)
  T5.1 Cross-cloud Exascale data access and processing
  T5.2 Metadata management and open data support for extreme collections
  T5.3 Structural metadata database support
  T5.4 Distributed encrypted storage for large scale sensitive data

## Slide 12: Deliverables – so far…

## Slide 13: Deliverables - future

## Slide 14: Milestone – up to now

## Slide 15: Milestone - Future

## Slide 16: This All-Hands…
Let’s start from the users needs
  We organized many “Users meet WP*” sessions
  address remaining issues
  clarify doubts
Let’s discuss in particular cross-WPs and cross-products issues
  Less pre-defined agenda, more discussion to converge
  We are few months away from the release